**JOB EXECUTION SCHEDULE FOR NON-MEDICAL EQUIPMENTS AND MEDICAL EQUIPMENT (FROM THE VENDORS)**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **SN** | **VENDOR** |  | **PROCUREMENT** | | | **INSTALLATION** | | |
|  |  |  | **START DATE** | **FINISH DATE** | **DURATION** | **START** | **FINISH DATE** | **DURATION** |
| 1 | REEDPRICEMAN | | 01-Mar-23 | 30-May-23 | 78 days (3M) | 26-May-23 | 20-Jul-23 | 48 days (1M 3WKS) |
| 2 | BLUEHUB | | 25-Feb-23 | 25-May-23 | 77 days (3M) | 26-May-23 | 05-Jul-23 | 35 days (1M 1WK) |
| 3 | SABTRAK | | No info | No info | At least 21 days (This is too vague. vendor should provide a comprehensive schedule with specific timelines) | No info | No info | At least 21 days (This is too vague. vendor should provide a comprehensive schedule with specific timelines) |
| 4 | SUPREME MEDITECH | PIPING | NIL | NIL | 3months |  |  | 2 Months |
| BEDHEAD SET & MEDICAL GAS STATIONS | NIL | NIL | 6 Months |  |  | 6 weeks (1M 2WKS) |