## SOH PHASE PLANNING TEMPLATE 1
STELLA OBASANJO HOSPITAL PHASE PLANNING
|  |  | FULL PROJECT 9-12 MONTHS | Option 1 (9-12 months) | Option 2 (6-9 Months) | Option 3 (6-9 Months) | Option 4 (6-7 Months)
|  | Description | FULL PROJECT WITH ADMIN | Full Project LESS ADMIN | OPD + DIAG/DIALYSIS/IVF/ER + MORTUARY + MEDICAL GASES | OPD + DIAG/DIALYSIS/IVF/ER + 36 SURGICAL + MEDICAL GASES | OPD + DIAG/DIALYSIS/IVF/ER
S/No. | CONTRACTOR | ITEMS
1 | A & K Construction Limited | OPD - Out Patient Department | 834452342.85 | 834452342.85 | 834452342.85 | 834452342.85 | 834452342.85
2 | A & K Construction Limited | IPD - In Patient Department | 3129724081.1 | 3129724081.1 | 1877834448.66 | 1784818356.3 | 1564862040.55
3 | A & K Construction Limited | Administrative Block | 2400786761.68 | 0 | 0 | 0 | 0
4 | TO BE ADVISED - TBA | Mortuary (Estimate) | 250000000 | 250000000 | 250000000 | 0 | 0
|  | SUB TOTAL - CONSTRUCTION | 6614963185.63 | 4214176423.95 | 2962286791.51 | 2619270699.15 | 2399314383.4
|  | Expected Construction Variation @10% | 661496318.563 | 421417642.395 | 296228679.151 | 261927069.915 | 239931438.34
|  | Construction Total | 7276459504.193 | 4635594066.345 | 3258515470.661 | 2881197769.065 | 2639245821.74
1 | SUDABELT MEDICAL CO. LTD | Lot 1 - Medical Equipment | 4135198000 | 4135198000 | 1566785650 | 1625778150 | 1566785650
2 | SUDABELT MEDICAL CO. LTD | Lot 2 - Radiology | 2104552000 | 2104552000 | 2104552000 | 2104552000 | 2104552000
3 | SUPREME MEDITECH LTD. | Lot 3 - Medical Gases | 648989222.31 | 648989222.31 | 648989222.31 | 648989222.31 | 0
4 | SUPREME MEDITECH LTD. | Lot 4 - Mortuary | 129241980 | 129241980 | 129241980 | 0 | 0
5 | SUDABELT MEDICAL CO. LTD | Lot 5 - Laboratory/IVF | 1090041596 | 1090041596 | 1090041596 | 1090041596 | 1090041596
6 | REEDPRICEMAN | KITCHEN LAUNDRY TOOLS + FURNITURE | 339472422.5 | 339472422.5 | 0 | 0 | 0
7 | BLUEHUB LTD | IT EQUIPMENT AND AUDIOVISUALS | 357722837.25 | 134105239.5 | 83156302.5 | 105440181.75 | 83156302.5
8 | SABTRAK LTD | APPLIANCES | 42407202 | 35573814 | 10870185 | 14850609 | 10870185
9 | REEDPRICEMAN | OFFICE FURNITURE | 1492211413 | 809369069.5 | 429106298.75 | 409710761.75 | 429106298.75
|  | EQUIPMENT AND FURNISHING SUB TOTAL | 10339836673.06 | 9426543343.81 | 6062743234.56 | 5999362520.81 | 5284512032.25
|  | Expected Equipment & Furnishing Variation@10% | 1033983667.306 | 942654334.381 | 606274323.456 | 599936252.081 | 528451203.225
|  | TOTAL EQUIPMENT AND FURNISHING COST | 11373820340.366 | 10369197678.191 | 6669017558.016 | 6599298772.891 | 5812963235.475
|  | SCENARIO TOTAL SUM | 18650279844.559 | 15004791744.536 | 9927533028.677 | 9480496541.956 | 8452209057.215
|  |  | DIFFERENCE | 3645488100.023 | 8722746815.882 | 9169783302.603 | 10198070787.344
EQUIPMENT PAYMENT PLAN
|  | Initial Payment (15 days) 60% | 6824292204.2196 | 6221518606.9146 | 4001410534.8096 | 3959579263.7346 | 3487777941.285
|  | Next Payment (60 days) 20% | 2274764068.0732 | 2073839535.6382 | 1333803511.6032 | 1319859754.5782 | 1162592647.095
|  | Final Payment (Post Deployment) 20% | 2274764068.0732 | 2073839535.6382 | 1333803511.6032 | 1319859754.5782 | 1162592647.095
This is excludes all Preoperational cost
APPROXIMATE ESTIMATED COST OF MORTUARY
Total floor area of OPD IS 2,458
Total contract sum of OPD IS 1,176,578,029.99
Cost per m2 cost/are= N478,672.92
| TOTAL FLOOR AREA OF MORTUARY SHOULD BE NO MORE THAN 550 M2 |  | TO BE REDESIGNED
Utilizing average cost Per Sq. metre of N445,545.00
This gives - N454,545.00 x 550 = N 250,000,000.00
Cost of constructing mortuary is N 250,000,000 - Estimated

## SOH PHASE 1(OPTION 3)
STELLA OBASANJO HOSPITAL PHASE PLANNING
|  |  | FULL PROJECT 9-12 MONTHS | Option 3 (6-9 Months)
|  | Description | FULL PROJECT WITH ADMIN | OPD + DIAG/DIALYSIS/IVF/ER + 36 SURGICAL + MEDICAL GASES
S/No. | CONTRACTOR | ITEMS
1 | A & K Construction Limited | OPD - Out Patient Department | 834452342.85 | 834452342.85
2 | A & K Construction Limited | IPD - In Patient Department | 3129724081.1 | 1784818356.3
3 | A & K Construction Limited | Administrative Block | 2400786761.68 | 0
4 | TO BE ADVISED - TBA | Mortuary (Estimate) | 250000000 | 0
|  | SUB TOTAL - CONSTRUCTION | 6614963185.63 | 2619270699.15
|  | Expected Construction Variation @10% | 661496318.563 | 261927069.915
|  | Construction Total | 7276459504.193 | 2881197769.065
1 | SUDABELT MEDICAL CO. LTD | Lot 1 - Medical Equipment | 4135198000 | 1625778150
2 | SUDABELT MEDICAL CO. LTD | Lot 2 - Radiology | 2104552000 | 2104552000
3 | SUPREME MEDITECH LTD. | Lot 3 - Medical Gases | 648989222.31 | 648989222.31
4 | SUPREME MEDITECH LTD. | Lot 4 - Mortuary | 129241980 | 0
5 | SUDABELT MEDICAL CO. LTD | Lot 5 - Laboratory/IVF | 1090041596 | 1090041596
6 | REEDPRICEMAN | KITCHEN LAUNDRY TOOLS + FURNITURE | 339472422.5 | 0
7 | BLUEHUB LTD | IT EQUIPMENT AND AUDIOVISUALS | 357722837.25 | 105440181.75
8 | SABTRAK LTD | APPLIANCES | 42407202 | 14850609
9 | REEDPRICEMAN | OFFICE FURNITURE | 1492211413 | 409710761.75
|  | EQUIPMENT AND FURNISHING SUB TOTAL | 10339836673.06 | 5999362520.81
|  | Expected Equipment & Furnishing Variation@10% | 1033983667.306 | 599936252.081
|  | TOTAL EQUIPMENT AND FURNISHING COST | 11373820340.366 | 6599298772.891
|  | SCENARIO TOTAL SUM | 18650279844.559 | 9480496541.956
|  |  | DIFFERENCE | 9169783302.603
EQUIPMENT PAYMENT PLAN
|  | Initial Payment (15 days) 60% | 6824292204.2196 | 3959579263.7346
|  | Next Payment (60 days) 20% | 2274764068.0732 | 1319859754.5782
|  | Final Payment (Post Deployment) 20% | 2274764068.0732 | 1319859754.5782
This is excludes all Preoperational cost
APPROXIMATE ESTIMATED COST OF MORTUARY
Total floor area of OPD IS 2,458
Total contract sum of OPD IS 1,176,578,029.99
Cost per m2 cost/are= N478,672.92
| TOTAL FLOOR AREA OF MORTUARY SHOULD BE NO MORE THAN 550 M2 |  | TO BE REDESIGNED
Utilizing average cost Per Sq. metre of N445,545.00
This gives - N454,545.00 x 550 = N 250,000,000.00
Cost of constructing mortuary is N 250,000,000 - Estimated