## Sheet1
SOH - ADMIN & IPD
ELALAN - RFI NO. 2
S/N | DESCRIPTION | ELALAN'S COMMENT | CONSULTANT'S RESPONSE
1 | Submission of Tender | Kindly confirm tender submission date.
2 | Site Visit | Site visit is required for better understanding of work scope. Kindly confirm when we can visit the site.
ADMIN BUILDING
3 | Modification/Correction of existing structural defects-(Item D. Page 2 ) | BOQ detail is very scanty. Kindly provide detailed description, drawings, pictures, etc. indicating the detail of work.
4 | Refurbish, rehabilitate and making good existing spiral staircases of Tread tapering 1200mm wide (28nr), with steel railing of 26m long including epoxy finishes - (Item N. Page 2) | Drawings and other details of the stair is required
SKY BRIDGE
5 | Fabricate and Install external diagonal steel panel trusses of (36 Panels) with support including all necessary bolts, accessories & fittings with attached 12mm tempered/toughened glasses (measured separately) - (Item A. Page 19) | Kindly avail us with Structural designs/details of the sky bridge.
6 | Fabricate GRP Seat overall size 1550mm x 4400mm including all necessary accessories and making good with mosaic tiles | Please clarify what this item of work is/supply a detailed design.
7 | Construct Concrete Platform (auditorium) & finishings of size 14000x2400mm including 2 steps of 2nr. | what is the depth of the concrete platform and what kind of finishing is expected on it?
8 | Structural Drawings | Kindly provide us with Structural Drawings for this project.
MEP WORKS
9 | PANELS AND DISTRIBUTION BOARDS | Could you please provide us with the schematic drawings for the Panel Boards, TV/Telephone panels (PABX) and Distribution Boards?
10 | LIGHT FITTINGS | Could you please provide us with the Lighting Legends/Datasheets?
11 | CABLES | Could you please clarify if the cable should be PVC/SWA/PVC OR PVC/PVC cable?
12 | We have noticed that this is an existing building | What is our exact scope of works, the BOQ’s received are incomplete and will not offer a commissioned system.
Please provide us with the detailed MEP drawings of this project for review