## Sheet1
WEEK | PROJECTED WEEKLY % TARGET | DATES | ACTUAL WEEKLY PERFORMANCE (%) | EXPECTED WEEKLY TARGET (%) | ACTIVITIES | RISK ASSESSMENT | RISK MTIGATION
WK 0 |  |  | 0 | 0
WK 1 (3%) 5DEC 22 | 3% | 5 DEC - 12 DEC | 48% | 48% | Mechanical first fix, electrical first fix, Firefighting first fix, Air conditioning first fix, Wall screeding, Internal plastering works, External plastering works, floor screeding, Pool wall and floor tiling, Special equipment MEPG piping works,Lift support fixation | (1)Alternative source of lighting & Illumination. (2)Reduction in manpower during Yelutide | (1) Coordination with EPUBMA for prompt resolution and implementation. (2) Coordinate with A & K to double workforce from 4th January
WK 2 (3%) |  | 12 DEC - 19 DEC | 50% | 51%
WK 3 (3%) |  | 19 DEC - 26 DEC | 52% | 54%
WK 4 (3%) |  | 26 DEC - 2 JAN | 54% | 57%
WK 5 (3%) | 3% | 2 JAN - 9 JAN | 55% | 60% | External plastering works, floor screeding, Cement, Sand and Water proofing, floor tiling, wall tiling, Pool wall and floor tiling, Metal works, Lift support fixation, , Primer painting, 1st & 2nd coat paintings, Furnishing, Vanity & Closets, Mechanical installation works, Electrical installation works.
WK 6 (3%) |  | 9 JAN - 16 JAN | 57.59% | 63%
WK 7 (3%) |  | 16 JAN - 23 JAN | 60.59% | 66%
WK 8 (3%) |  | 23 JAN - 30 JAN | 61.64% | 69%
WK 9 (1.5%) | 1.5% | 30 JAN - 6 FEB |  | 70.5% | Suspended ceiling,Doors & Windows, Reception Counter & Kitchen cabinets, Mechanical shaft works, Electrical shaft works, Firefighting shaft works, Air-conditioning shaft works, Eletrical installations, mechanical installations,Firefighting installation, Air-condition installation, Pool Piping, Pump & Filtration Installation, Special equipment MEPG installations
WK 10 (1.5%) |  | 6 FEB - 13 FEB |  | 72%
WK 11 (1.5%) |  | 13 FEB - 20 FEB |  | 73.5%
WK 12 (1.5%) |  | 20 FEB - 27 FEB |  | 75%
WK 13 (5.25%) | 5.25% | 27 FEB - 6 MAR |  | 80.25% | Suspended ceiling,Eletrical installations, mechanical installations, Firefighting installation, Pool Piping, Pump & Filtration Installation, Special equipment MEPG installations. Testing, commissioning, handing over
WK 14 (5.25%) |  | 6 MAR - 13 MAR |  | 85.5%
WK 15 (5.25%) |  | 13 MAR - 20 MAR |  | 90.75%
WK 16 (5.25%) |  | 20 MAR - 27 MAR |  | 96%
WK 17 (1%) | 1% | 27 MAR - 3 APR |  | 97% | Eletrical installations, mechanical installations, Firefighting installation, Pool Piping, Pump & Filtration Installation, Special equipment MEPG installations. Testing, commissioning, handing over
WK 18 (1%) |  | 3 APR - 10 APR |  | 98%
WK 19 (1%) |  | 10 APR - 17 APR |  | 99%
WK 20 (1%) 24APR 23 |  | 17 APR - 24 APR |  | 100%
WKS
7.36%

## Sheet2
S/N | ACTIVITY | START DATE | FINISH DATE
1 | SPECIAL MEPF SHOP DRAWING PREPARATION, SUBMITTAL AND APPROVAL | 2022-12-01 | 2022-12-10
1.1 | Mechanical shop drawings | 2022-12-01 | 2022-12-10
1.2 | Electrical shop drawings | 2022-12-01 | 2022-12-10
1.3 | Air-conditioning shop drawings | 2022-12-01 | 2022-12-10
1.4 | Firefighting shop drawings | 2022-12-01 | 2022-12-10
2 | GENERAL MEPF FIRST FIX | 2022-12-03 | 2022-12-27
2.1 | Mechanical first fix | 2022-12-10 | 2022-12-27
2.2 | Electrical first fix | 2022-12-10 | 2022-12-27
2.3 | Firefighting first fix | 2022-12-10 | 2022-12-27
2.4 | Air conditioning first fix | 2022-12-10 | 2022-12-27
3 | PLASTERING | 2022-12-01 | 2023-01-30
3.1 | Wall screeding | 2022-12-01 | 2022-12-27
3.2 | Internal plastering works | 2022-12-20 | 2023-01-18
3.3 | External plastering works | 2022-12-27 | 2023-01-21
3.4 | Floor screeding | 2023-01-05 | 2023-01-30
4 | WATER PROOFING | 2023-01-16 | 2023-01-30
4.1 | Cement, Sand and Water proofing | 2023-01-16 | 2023-01-30
5 | FINISHINGS | 2023-01-11 | 2023-04-04
5.1 | Floor tiling | 2023-01-11 | 2023-01-30
5.2 | Wall tiling | 2023-01-11 | 2023-01-30
5.3 | Doors & Windows | 2023-02-18 | 2023-03-03
5.4 | Metal works | 2023-01-30 | 09-Feb-23
5.5 | Suspended ceiling | 2023-02-06 | 28-Feb-23
5.6 | Furnishing, Vanity & Closets | 2023-02-13 | 2023-02-28
5.7 | Reception Counter & Kitchen cabinets | 2023-03-01 | 2023-03-22
5.8 | Primer painting | 2023-01-18 | 2023-02-02
5.9 | 1st & 2nd coat paintings | 2023-02-06 | 2023-02-21
5.1 | Final painting | 2023-03-25 | 2023-04-04
6 | MEPF SHAFT WORKS | 2023-03-01 | 2023-03-07
6.1 | Mechanical shaft works | 2023-03-01 | 2023-03-07
6.2 | Electrical shaft works | 2023-03-01 | 2023-03-07
6.3 | Firefighting shaft works | 2023-03-01 | 2023-03-07
6.4 | Air conditioning shaft works | 2023-03-01 | 2023-03-07
7 | MEPF INSTALLATION WORK | 2023-02-02 | 2023-04-04
7.1 | Mechanical installation | 2023-02-15 | 04-Apr-23
7.2 | Electrical works installation | 2023-02-02 | 04-Apr-23
7.3 | Firefighting installation | 2023-03-08 | 2023-04-04
7.4 | Air conditioning installation | 2023-03-08 | 2023-03-21
8 | LIFT SUPPORT FIXATION | 08-Dec-22 | 05-Jan-23
8.1 | Lift support fixation | 08-Dec-22 | 05-Jan-23
9 | HYDROTHERAPY POOL | 2023-01-11 | 2023-03-30
9.1 | Pool wall and floor tiling | 2023-01-11 | 2023-01-21
9.2 | Pool Piping, Pump & Filtration Installation | 2023-03-08 | 2023-03-30
10 | SPECIAL EQUIPMENT INSTALLATION | 2022-12-10 | 2022-04-04
10.1 | Special equipment MEPG piping works | 2022-12-10 | 2022-12-27
10.2 | Special equipment MEPG installations | 2023-02-15 | 2023-04-04
11 | OPD TESTING AND COMMISSIONING HANDING OVER | 2023-04-05 | 2023-04-28
11.1 | Testing, commissioning and handing over | 2023-04-05 | 2023-04-28

## Sheet3
SN | QTRS | TASK/ACTIVITY |  | START DATE | END DATE | DAYS | EXPECTED TARGET (%)
|  | OPD | IPD
1 | QTR 1 | Internal & External plastering works. General MEPF first fix | NA | 2023-01-01 | 2023-01-31 | 31 | 3 | Internal & External plastering works, floor screeding, Cement, Sand and Water proofing, floor tiling, wall tiling, Pool wall and floor tiling, Metal works, Lift support fixation,Primer painting,Lifting equipment , General MEPF first fix
2 |  | Internal & External plastering works. General MEPF first fix. Re-issuance of contract award for medical and non-medical equipments and mobilisation. | Re-issuance of contract award for medical and non-medical equipments and mobilisation. | 2023-02-01 | 2023-02-28 | 28 | 4 | Doors and windows, metal works, Suspended ceiling, 1st & 2nd coat painting, Furnishing, Vanity & Closets, MEPF shaft works, General MEPF first fix, Re-issuance of contract award for medical and non-medical equipments.
3 |  | Internal & External plastering works. Floor screeding, Cement, Sand and Water proofing, floor tiling, wall tiling, Pool wall and floor tiling, Metal works, Lift support fixation,Primer painting,Lifting equipment. Procurement of medical and non-medical equipments. | MEPF & G shop drawings. Walls and partition alteration, Windows, doors, suspended ceiling and floor alterations, air-condition, mechanical and electrical alterations. Painting and metal works. Masonry and internal partition works, thermal and moisture (water proofing). Procurement of medical and non-medical equipments. | 2023-03-01 | 2023-03-31 | 31 | 13 | Suspended ceiling,Doors & Windows, Reception Counter & Kitchen cabinets,MEPF shaft works, General MEPF second fix, Pool Piping, Pump & Filtration Installation, Final painting. Procurement of medical and non-medical equipments.
4 | QTR 2 | Floor tiling, wall tiling, Pool wall and floor tiling.Doors and windows, metal works, Suspended ceiling, 1st & 2nd coat painting, Furnishing, Vanity & Closets, MEPF second fix. MEPF shaft works. Procurement of medical and non-medical equipments. | General and special MEPF first fix,Thermal and moisture (water proofing),Masonry and internal partition works, Door and windows. Lift wall. Construction of sky bridge. Procurement of medical and non-medical equipments. External works. | 2023-04-01 | 2023-04-30 | 30 | 11 | MEPF Second fix.Final painting. Procurement of medical and non-medical equipment.
5 |  | Suspended ceiling,Doors & Windows, Reception Counter & Kitchen cabinets,MEPF shaft works, General MEPF second fix, Pool Piping, Pump & Filtration Installation, Final painting. Procurement of medical and non-medical equipments. | General and Special MEPF first fix, Masonry and internal partition works, Doors and windows, Painting. Lift support fixation. Construction of sky bridge. Construction of medical gas and UPS housings. Medical gas piping. Procurement of medical and non-medical equipments. Special medical equipment room preparation. External works | 2023-05-01 | 2023-05-31 | 31 | 14 | MEPF final fix, Final painting, Pool Piping, Pump & Filtration Installation,Procurement of medical and non-medical equipment.
6 |  | MEPF final fix. Pool Piping, Pump & Filtration Installation Final painting. Installation of medical and non-medical equipment installations. | Floor and wall tiling. Doors and windows. Suspended ceiling installation. Fitting and fixtures. Metal works. Painting. MEP second fix. Procurement of medical and non-medical equipments. Construction of housing for RO. Medical gas piping. Lifting equipment. Construction of sky bridge. External works. Special medical equipment room preparation.. External works. | 2023-06-01 | 2023-06-30 | 30 | 12 | MEPF final fix, Final painting. Installation of medical and non-medical equipment installations.
7 | QTR 3 | MEPF final fix, Final painting, Installation of medical and non-medical equipments . | Floor and wall tiling. Doors and windows. Suspended ceiling installation. Fitting and fixtures. Metal works. Painting. MEP final fix. Lifting equipment. Medical and non-medical equipment installation. External works | 2023-07-01 | 2023-07-31 | 31 | 11 | MEPF final fix, Final painting, Installation of medical and non-medical equipments .
8 |  | Installation of Medical Equipment. Training of personnel. Testing, commissioning, and handing over. | Final painting. Medical and non-medical Equipment installation | 2023-08-01 | 2023-08-31 | 31 | 10 | Medical Equipment installation.Training of personnel. Testing, commissioning, and handing over.
9 |  | NA | Final painting. Medical and non-medical Equipment installation. Training of personnel | 2023-09-01 | 31-September-2023 | 31 | 9 | NA
10 | QTR4 | NA | Medical and non-medical Equipment installation. | 2023-10-01 | 2023-10-31 | 9 | 8 | NA
11 |  | NA | Medical Equipment installation and Testing. Training of personnel, commissioning and handing over | 2023-11-01 | 2023-11-30 | 30 | 5 | NA
100
[9 empty] | Month | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov
[9 empty] | Montthly | 3% | 4% | 13% | 11% | 14% | 12% | 11% | 10% | 9% | 8% | 5%
[9 empty] | Cummilative | 3% | 7% | 20% | 31% | 45% | 57% | 68% | 78% | 87% | 95% | 100%