## Sheet1
WEEK | PROJECTED WEEKLY % TARGET | DATES | ACTUAL WEEKLY PERFORMANCE (%) | EXPECTED WEEKLY TARGET (%) | ACTIVITIES | RISK ASSESSMENT | RISK MTIGATION
WK 0 |  |  | 0 | 0
WK 1 (3%) 5DEC 22 | 3% | 5 DEC - 12 DEC | 48% | 48% | Mechanical first fix, electrical first fix, Firefighting first fix, Air conditioning first fix, Wall screeding, Internal plastering works, External plastering works, floor screeding, Pool wall and floor tiling, Special equipment MEPG piping works,Lift support fixation | (1)Alternative source of lighting & Illumination. (2)Reduction in manpower during Yelutide | (1) Coordination with EPUBMA for prompt resolution and implementation. (2) Coordinate with A & K to double workforce from 4th January
WK 2 (3%) |  | 12 DEC - 19 DEC | 50% | 51%
WK 3 (3%) |  | 19 DEC - 26 DEC | 52% | 54%
WK 4 (3%) |  | 26 DEC - 2 JAN | 54% | 57%
WK 5 (3%) | 3% | 2 JAN - 9 JAN | 55% | 60% | External plastering works, floor screeding, Cement, Sand and Water proofing, floor tiling, wall tiling, Pool wall and floor tiling, Metal works, Lift support fixation, , Primer painting, 1st & 2nd coat paintings, Furnishing, Vanity & Closets, Mechanical installation works, Electrical installation works.
WK 6 (3%) |  | 9 JAN - 16 JAN | 57.59% | 63%
WK 7 (3%) |  | 16 JAN - 23 JAN | 60.59% | 66%
WK 8 (3%) |  | 23 JAN - 30 JAN | 61.64% | 69%
WK 9 (1.5%) | 1.5% | 30 JAN - 6 FEB |  | 70.5% | Suspended ceiling,Doors & Windows, Reception Counter & Kitchen cabinets, Mechanical shaft works, Electrical shaft works, Firefighting shaft works, Air-conditioning shaft works, Eletrical installations, mechanical installations,Firefighting installation, Air-condition installation, Pool Piping, Pump & Filtration Installation, Special equipment MEPG installations
WK 10 (1.5%) |  | 6 FEB - 13 FEB |  | 72%
WK 11 (1.5%) |  | 13 FEB - 20 FEB |  | 73.5%
WK 12 (1.5%) |  | 20 FEB - 27 FEB |  | 75%
WK 13 (5.25%) | 5.25% | 27 FEB - 6 MAR |  | 80.25% | Suspended ceiling,Eletrical installations, mechanical installations, Firefighting installation, Pool Piping, Pump & Filtration Installation, Special equipment MEPG installations. Testing, commissioning, handing over
WK 14 (5.25%) |  | 6 MAR - 13 MAR |  | 85.5%
WK 15 (5.25%) |  | 13 MAR - 20 MAR |  | 90.75%
WK 16 (5.25%) |  | 20 MAR - 27 MAR |  | 96%
WK 17 (1%) | 1% | 27 MAR - 3 APR |  | 97% | Eletrical installations, mechanical installations, Firefighting installation, Pool Piping, Pump & Filtration Installation, Special equipment MEPG installations. Testing, commissioning, handing over
WK 18 (1%) |  | 3 APR - 10 APR |  | 98%
WK 19 (1%) |  | 10 APR - 17 APR |  | 99%
WK 20 (1%) 24APR 23 |  | 17 APR - 24 APR |  | 100%
WKS
[9 empty] | Month | 2022 | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov
[6 empty] | 7.36% |  | OPD + IPD | Monthly |  | 4% | 3% | 10% | 16% | 16% | 10% | 10% | 9% | 1.5% | 1.5% | 1%
[9 empty] | Cummilative | 18% | 22% | 25% | 35% | 51% | 67% | 77% | 87% | 96% | 97.5% | 99% | 100%
[8 empty] | OPD | Monthly

## Sheet2
S/N | ACTIVITY | START DATE | FINISH DATE
1 | SPECIAL MEPF SHOP DRAWING PREPARATION, SUBMITTAL AND APPROVAL | 2022-12-01 | 2022-12-10
1.1 | Mechanical shop drawings | 2022-12-01 | 2022-12-10
1.2 | Electrical shop drawings | 2022-12-01 | 2022-12-10
1.3 | Air-conditioning shop drawings | 2022-12-01 | 2022-12-10
1.4 | Firefighting shop drawings | 2022-12-01 | 2022-12-10
2 | GENERAL MEPF FIRST FIX | 2022-12-03 | 2022-12-27
2.1 | Mechanical first fix | 2022-12-10 | 2022-12-27
2.2 | Electrical first fix | 2022-12-10 | 2022-12-27
2.3 | Firefighting first fix | 2022-12-10 | 2022-12-27
2.4 | Air conditioning first fix | 2022-12-10 | 2022-12-27
3 | PLASTERING | 2022-12-01 | 2023-01-30
3.1 | Wall screeding | 2022-12-01 | 2022-12-27
3.2 | Internal plastering works | 2022-12-20 | 2023-01-18
3.3 | External plastering works | 2022-12-27 | 2023-01-21
3.4 | Floor screeding | 2023-01-05 | 2023-01-30
4 | WATER PROOFING | 2023-01-16 | 2023-01-30
4.1 | Cement, Sand and Water proofing | 2023-01-16 | 2023-01-30
5 | FINISHINGS | 2023-01-11 | 2023-04-04
5.1 | Floor tiling | 2023-01-11 | 2023-01-30
5.2 | Wall tiling | 2023-01-11 | 2023-01-30
5.3 | Doors & Windows | 2023-02-18 | 2023-03-03
5.4 | Metal works | 2023-01-30 | 09-Feb-23
5.5 | Suspended ceiling | 2023-02-06 | 28-Feb-23
5.6 | Furnishing, Vanity & Closets | 2023-02-13 | 2023-02-28
5.7 | Reception Counter & Kitchen cabinets | 2023-03-01 | 2023-03-22
5.8 | Primer painting | 2023-01-18 | 2023-02-02
5.9 | 1st & 2nd coat paintings | 2023-02-06 | 2023-02-21
5.1 | Final painting | 2023-03-25 | 2023-04-04
6 | MEPF SHAFT WORKS | 2023-03-01 | 2023-03-07
6.1 | Mechanical shaft works | 2023-03-01 | 2023-03-07
6.2 | Electrical shaft works | 2023-03-01 | 2023-03-07
6.3 | Firefighting shaft works | 2023-03-01 | 2023-03-07
6.4 | Air conditioning shaft works | 2023-03-01 | 2023-03-07
7 | MEPF INSTALLATION WORK | 2023-02-02 | 2023-04-04
7.1 | Mechanical installation | 2023-02-15 | 04-Apr-23
7.2 | Electrical works installation | 2023-02-02 | 04-Apr-23
7.3 | Firefighting installation | 2023-03-08 | 2023-04-04
7.4 | Air conditioning installation | 2023-03-08 | 2023-03-21
8 | LIFT SUPPORT FIXATION | 08-Dec-22 | 05-Jan-23
8.1 | Lift support fixation | 08-Dec-22 | 05-Jan-23
9 | HYDROTHERAPY POOL | 2023-01-11 | 2023-03-30
9.1 | Pool wall and floor tiling | 2023-01-11 | 2023-01-21
9.2 | Pool Piping, Pump & Filtration Installation | 2023-03-08 | 2023-03-30
10 | SPECIAL EQUIPMENT INSTALLATION | 2022-12-10 | 2022-04-04
10.1 | Special equipment MEPG piping works | 2022-12-10 | 2022-12-27
10.2 | Special equipment MEPG installations | 2023-02-15 | 2023-04-04
11 | OPD TESTING AND COMMISSIONING HANDING OVER | 2023-04-05 | 2023-04-28
11.1 | Testing, commissioning and handing over | 2023-04-05 | 2023-04-28

## Sheet3
WEEK | START DATE | END DATE | TASK/ACTIVITY | % COMPLETION | ACTUAL CUMILATIVE TARGET (%) | EXPECTED CUMILATIVE TARGET (%) | CHALLENGES | SOLUTIONS
6 | 2023-02-01 | 2023-02-28 | Internal & External plastering works. | 63 | 65 | 70 | Reduction in manpower during Yelutide of December 2022 | Coordinate with A & K to double workforce & organize a recovery plan
|  |  | General MEPF first fix. | 80 |  |  | The current CBN monetry policy has affected the payment process to casual workers (These workers constitute 80% of the workforce on site). Which has led to mass exodus of these workers
IPD
WEEK | START DATE | END DATE | TASK/ACTIVITY | % COMPLETION | ACTUAL CUMILATIVE TARGET (%) | EXPECTED CUMILATIVE TARGET (%) | CHALLENGES | SOLUTIONS
6 | 2023-02-01 | 2023-02-28 | Awaiting contractor mobilization | 1 | 1 | 1 | Mobization | Coordinating with MOH on project phasing options
|  |  | Equipment | [6 empty] | Month | 2022 | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov
WEEK | START DATE | END DATE | TASK/ACTIVITY | COMPLETION LEVEL | ACTUAL CUMILATIVE TARGET (%) | EXPECTED CUMILATIVE TARGET (%) | CHALLENGES | SOLUTIONS | OPD + IPD | Monthly |  | 4% | 3% | 10% | 16% | 16% | 10% | 10% | 9% | 1.5% | 1.5% | 1%
[10 empty] | Cummilative | 18% | 22% | 25% | 35% | 51% | 67% | 77% | 87% | 96% | 97.5% | 99% | 100%
6 | 2023-02-01 | 2023-02-28 | Conclude all necessary documentation with approved vendors for medical and non-medical equipment and financial mobilization. | 1 | 1 | 1 | Mobization | Coordinating with MOH on project phasing options | OPD | Monthly
[10 empty] | Cummilative | 35% | 43% | 48% | 53% | 69% | 88% | 94% | 97% | 100%
[9 empty] | IPD | Monthly | [8 empty] | 96% | 97.5% | 99% | 100%
[10 empty] | Cummilative | 0% | 0% | 1% | 17% | 31% | 46% | 58% | 75% | 92% | 97% | 98.5% | 100%
WEEK | START DATE | SUBMITALLS |  | CHALLENGES | SOLUTIONS
OPD
|  | INVOICE | SUPPLY SCHEDULE
6 | BLUEHUB LTD | SUBMITTED | PENDING | NIL | NIL
| REEDPRICEMAN | SUBMITTED | SUBMITTED
| SABTRAK LTD | PENDING | PENDING
| SUDABELT MEDICAL CO. LTD | PENDING | PENDING
| SUPREME MEDITECH LTD | PENDING | PENDING
IPD