## wk detailed
QTR | MONTH |  | TASK/ACTIVITY | [6 empty] | EXPECTED WEEKLY TARGET (%) | EXPECTED MONTHLY TARGET (%) | EXPECTED CUMULATIVE TARGET (%)
OPD
|  |  | Activity | Activity (%) | Weekly (%) | Monthly (%) | Cummulative (%) | IPD | %
QTR 1 | JAN | WK 1 (2-7) | NIL |  |  |  |  | NIL |  | 1 | 4 | 22
|  | WK 2 (9-14) | External plastering works |  |  |  |  | NIL |  | 1
|  |  | General MEPF first fix |  |  |  |  | NIL
|  | WK 3 (16 -21) | Internal & External plastering works |  |  |  |  | NIL |  | 1
|  |  | General MEPF first fix |  |  |  |  | NIL
|  | WK 4(23 - 28) | Internal & External plastering works |  |  |  |  | NIL |  | 1
|  |  | General MEPF first fix |  |  |  |  | NIL
| FEB | WK 5 (30 - 4) | Internal & External plastering works |  | 1.25 | 5 | 44.25 | Conclude all necessary documentation with approved vendors for medical and non-medical equipments and financial mobilisation. |  |  | 3 | 25
General MEPF first fix
|  |  | Conclude all necessary documentation with approved vendors for medical and non-medical equipments and financial mobilisation. | [10 empty] | 1.25
|  | WK 6 (6-11) | Internal & External plastering works |  | 1.25 |  | 45.5
General MEPF first fix
|  |  | Conclude all necessary documentation with approved vendors for medical and non-medical equipments and financial mobilisation. | [10 empty] | 47
|  | WK 7 (13-18) | Internal & External plastering works |  | 1.25 |  | 46.75
General MEPF first fix
Conclude all necessary documentation with approved vendors for medical and non-medical equipments and financial mobilisation.
|  | WK 8 (20-25) | Internal & External plastering works |  | 1.25 |  | 48
General MEPF first fix
Conclude all necessary documentation with approved vendors for medical and non-medical equipments and financial mobilisation.
| MAR | WK 9 (27-4) | Internal & External plastering works |  |  |  |  | Demolition and removal of existing walls |  |  | 10 | 35
|  |  | General MEPF first fix |  |  |  |  | Demolition of existing internal walls
Procurement of medical and non-medical equipments.
Lift support fixation
|  | WK 10 (6-11) | Internal & External plastering works |  |  |  |  | Demolition and removal of existing walls
|  |  | General MEPF first fix |  |  |  |  | Demolition of existing internal walls
|  |  | Procurement of medical and non-medical equipments. |  |  |  |  | Removal of existing suspended ceiling
Careful removal of existing doors & windows
Scraping of internal painting work
Careful removal of existing hand rails
|  |  | Lift support fixation |  |  |  |  | Lift wall re-inforcement installation
|  | WK 11 (13-18) | External plastering works |  |  |  |  | Demolition and removal of existing walls
|  |  | Procurement of medical and non-medical equipments. |  |  |  |  | Demolition of existing internal walls
|  |  | Cement, Sand and Water proofing |  |  |  |  | Removal of existing suspended ceiling
|  |  | Metal works |  |  |  |  | Careful removal of existing doors & windows
|  |  | Lift support fixation |  |  |  |  | Scraping of internal painting work
Careful removal of existing hand rails
Removal of floor tiles at stairs
Stripping of existing floor tiles
Careful removal of existing cables and peripherals, DBs and panels
Lift wall formwork installation
Lift wall re-inforcement installation
Excavation of footings and tie beams for RO, UPS & gas rooms
Column & beams, backfiling & compacting for RO, UPS & gas rooms
Doors & windows for RO, UPS & gas rooms
|  | WK 12 (20-25) | External plastering works |  |  |  |  | Demolition and removal of existing walls
|  |  | Cement, Sand and Water proofing |  |  |  |  | Demolition of existing internal walls
|  |  | Metal works |  |  |  |  | Removal of existing suspended ceiling
|  |  | Floor screeding |  |  |  |  | Careful removal of existing doors & windows
|  |  | Procurement of medical and non-medical equipments. |  |  |  |  | Scraping of internal painting work
Careful removal of existing hand rails
Removal of floor tiles at stairs
Stripping of existing floor tiles
Careful removal of existing cables and peripherals, DBs and panels
Lift wall casting
Lift wall formwork installation
Lift wall re-inforcement installation
Foundation works for RO, UPS & gas rooms
Column & beams, backfiling & compacting for RO, UPS & gas rooms
Doors & windows for RO, UPS & gas rooms
Excavation of footings and tie beams for RO, UPS & gas rooms
|  | WK 13 (27-1) | Cement, Sand and Water proofing |  |  |  |  | Demolition and removal of existing walls
|  |  | Floor screeding |  |  |  |  | Demolition of existing internal walls
|  |  | Metal works |  |  |  |  | Removal of existing suspended ceiling
|  |  | Floor & wall tiling |  |  |  |  | Careful removal of existing doors & windows
|  |  | Reception counter and kitchen cabinets |  |  |  |  | Scraping of internal painting work
|  |  | Primer painting |  |  |  |  | Careful removal of existing hand rails
|  |  | Aluminium Doors and windows |  |  |  |  | Removal of floor tiles at stairs
|  |  | Lifting equipment |  |  |  |  | Stripping of existing floor tiles
|  |  | Procurement of medical and non-medical equipments. |  |  |  |  | Careful removal of existing cables and peripherals, DBs and panels
Lift wall casting
Lift wall formwork installation
Lift wall re-inforcement installation
Block work and internal partitions
Foundation works for RO, UPS & gas rooms
Column & beams, backfiling & compacting for RO, UPS & gas rooms
Doors & windows for RO, UPS & gas rooms
QTR 2 | APR | WK 14 (3-8) | Metal works |  |  |  |  | Demolition and removal of existing walls |  |  | 16 | 51
|  |  | Aluminium Doors and windows |  |  |  |  | Demolition of existing internal walls
|  |  | Lifting equipment |  |  |  |  | Removal of existing suspended ceiling
|  |  | Primer painting |  |  |  |  | Careful removal of existing doors & windows
|  |  | 1st & 2nd coat painting, |  |  |  |  | Scraping of internal painting work
|  |  | Floor & wall tiling |  |  |  |  | Careful removal of existing hand rails
|  |  | Floor screeding |  |  |  |  | Removal of floor tiles at stairs
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Stripping of existing floor tiles
|  |  | Reception counter and kitchen cabinets |  |  |  |  | Careful removal of existing cables and peripherals, DBs and panels
Special MEPF first fix
Medical gas installation
Lift wall formwork installation
Lift wall casting
Lift wall re-inforcement installation
Block work and internal partitions
Column & beams, backfiling & compacting for RO, UPS & gas rooms
Cement, Sand & Waterproofing for RO, UPS & Gas rooms
Doors & windows for RO, UPS & gas rooms
|  | WK 15 (10-15) | Metal works |  |  |  |  | Demolition and removal of existing walls
|  |  | Lifting equipment |  |  |  |  | Demolition of existing internal walls
|  |  | Primer painting |  |  |  |  | Removal of existing suspended ceiling
|  |  | Reception counter and kitchen cabinets |  |  |  |  | Careful removal of existing hand rails
|  |  | 1st & 2nd coat painting, |  |  |  |  | Removal of floor tiles at stairs
|  |  | Floor & wall tiling |  |  |  |  | Stripping of existing floor tiles
|  |  | Floor screeding |  |  |  |  | Careful removal of existing cables and peripherals, DBs and panels
|  |  | General electrical second fix |  |  |  |  | Special MEPF first fix
|  |  | MEPF shaft works |  |  |  |  | Medical gas installation
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Lift wall formwork installation
Lift wall casting
Lift wall re-inforcement installation
Block work and internal partitions
Checking integrity of mechanical works
Checking integrity of electrical works
Column & beams, backfiling & compacting for RO, UPS & gas rooms
Doors & windows for RO, UPS & gas rooms
|  | WK 16 (17-22) | Metal works |  |  |  |  | Demolition of existing internal walls
|  |  | Lifting equipment |  |  |  |  | Removal of existing suspended ceiling
|  |  | Primer painting |  |  |  |  | Careful removal of existing doors & windows
|  |  | 1st & 2nd coat painting, |  |  |  |  | Scraping of internal painting work
|  |  | Reception counter and kitchen cabinets |  |  |  |  | Careful removal of existing hand rails
|  |  | Floor & wall tiling |  |  |  |  | Removal of floor tiles at stairs
|  |  | Floor screeding |  |  |  |  | Stripping of existing floor tiles
|  |  | General electrical second fix |  |  |  |  | Careful removal of existing cables and peripherals, DBs and panels
|  |  | MEPF shaft works |  |  |  |  | Special MEPF first fix
|  |  | Pool wall tiling |  |  |  |  | Medical gas installation
|  |  | Pool floor tiling |  |  |  |  | Lift wall casting
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Lift wall formwork installation
Block work and internal partitions
Cement, sand and water profing
Doors subframes installation
Checking integrity of mechanical works
Refurbish existing mechanical lines
Checking integrity of electrical works
Checking integrity of fire fighting works
Checking integrity, installation and refurbishing of HVAC works
Column & beams, backfiling & compacting for RO, UPS & gas rooms
Doors & windows for RO, UPS & gas rooms
|  | WK 17 (24-29) | Lifting equipment |  |  |  |  | Scraping of internal painting work
|  |  | 1st & 2nd coat painting, |  |  |  |  | Careful removal of existing hand rails
|  |  | Floor tiling |  |  |  |  | Removal of floor tiles at stairs
|  |  | General electrical second fix |  |  |  |  | Stripping of existing floor tiles
|  |  | General mechanical second fix |  |  |  |  | Careful removal of existing cables and peripherals, DBs and panels
|  |  | MEPF shaft works |  |  |  |  | Special MEPF first fix
|  |  | Pool wall tiling |  |  |  |  | Medical gas installation
|  |  | Pool floor tiling |  |  |  |  | Lift wall casting
|  |  | Furnishing, Vanity & Closets |  |  |  |  | Lift wall formwork installation
|  |  | Reception counter and kitchen cabinets |  |  |  |  | Block work and internal partitions
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Cement, sand and water profing
Doors subframes installation
Checking integrity of mechanical works
Refurbish existing mechanical lines
Checking integrity of electrical works
Checking integrity of fire fighting works
Checking integrity, installation and refurbishing of HVAC works
Column & beams, backfiling & compacting for RO, UPS & gas rooms
Doors & windows for RO, UPS & gas rooms
| MAY | WK 18 (1-6) | General electrical second fix |  |  |  |  | Special MEPF first fix |  |  | 16 | 67
|  |  | General mechanical second fix |  |  |  |  | Medical gas installation
|  |  | HVAC installation |  |  |  |  | Lift wall casting
|  |  | Fire-fighting installation |  |  |  |  | Lift wall formwork installation
|  |  | MEPF shaft works |  |  |  |  | Block work and internal partitions
|  |  | Suspended ceiling |  |  |  |  | Cement, sand and water profing
|  |  | Furnishing, Vanity & Closets |  |  |  |  | Doors subframes installation
|  |  | Pool Piping, Pump & Filtration Installation |  |  |  |  | Checking integrity of mechanical works
|  |  | Reception counter and kitchen cabinets |  |  |  |  | Refurbish existing mechanical lines
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Checking integrity of electrical works
Checking integrity of fire fighting works
Checking integrity, installation and refurbishing of HVAC works
Column & beams, backfiling & compacting for RO, UPS & gas rooms
Floor Screeding works for RO, UPS & gas rooms
Doors & windows for RO, UPS & gas rooms
MEPF second and final fixes for RO, UPS & gas rooms
|  | WK 19 (8-13) | General electrical second and final fix |  |  |  |  | Special MEPF first fix
|  |  | HVAC installation |  |  |  |  | Medical gas installation
|  |  | Fire-fighting installation |  |  |  |  | Lift wall casting
|  |  | General mechanical second fix |  |  |  |  | Lift wall formwork installation
|  |  | MEPF shaft works |  |  |  |  | Block work and internal partitions
|  |  | Furnishing, Vanity & Closets |  |  |  |  | Checking integrity of mechanical works
|  |  | Suspended ceiling |  |  |  |  | Refurbish existing mechanical lines
|  |  | Reception counter and kitchen cabinets |  |  |  |  | Checking integrity of electrical works
|  |  | Pool Piping, Pump & Filtration Installation |  |  |  |  | Column & beams, backfiling & compacting for RO, UPS & gas rooms
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Checking integrity of fire fighting works
Slab work for for RO, UPS & gas rooms
Floor Screeding works for RO, UPS & gas rooms
Doors & windows for RO, UPS & gas rooms
MEPF second and final fixes for RO, UPS & gas rooms
Parapet Work in RO, UPS & gas rooms
Checking integrity, installation and refurbishing of HVAC works
|  | WK 20 (15-20) | General electrical final fix |  |  |  |  | Medical gas installation
|  |  | HVAC installation |  |  |  |  | Lift wall casting
|  |  | Fire-fighting installation |  |  |  |  | Lift wall formwork installation
|  |  | General mechanical second fix |  |  |  |  | Internal plaster and related works
|  |  | MEPF shaft works |  |  |  |  | Refurbish existing mechanical lines
|  |  | Furnishing, Vanity & Closets |  |  |  |  | Checking integrity of fire fighting works
|  |  | Suspended ceiling |  |  |  |  | Checking integrity, installation and refurbishing of HVAC works
|  |  | Pool Piping, Pump & Filtration Installation |  |  |  |  | Block work and internal partitions
|  |  | Reception counter and kitchen cabinets |  |  |  |  | Cement, sand and water profing
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Column & beams, backfiling & compacting for RO, UPS & gas rooms
Slab work for for RO, UPS & gas rooms
Blockworks and Internal Partition Boards for RO,UPS & gas rooms
Floor Screeding works for RO, UPS & gas rooms
Doors & windows for RO, UPS & gas rooms
Stairs Ballustrades and Handrailling for RO, UPS & gas rooms
MEPF second and final fixes for RO, UPS & gas rooms
Parapet Work in RO, UPS & gas rooms
Doors subframes installation
|  | WK 21 (22-27) | General electrical final fix |  |  |  |  | Medical gas installation
|  |  | Suspended ceiling |  |  |  |  | Lift wall casting
|  |  | Pool Piping, Pump & Filtration Installation |  |  |  |  | Lift wall formwork installation
|  |  | Reception counter and kitchen cabinets |  |  |  |  | Block work and internal partitions
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | External plaster and related works
Slab work for for RO, UPS & gas rooms
Blockworks and Internal Partition Boards for RO,UPS & gas rooms
Doors & windows for RO, UPS & gas rooms
Stairs Ballustrades and Handrailling for RO, UPS & gas rooms
MEPF second and final fixes for RO, UPS & gas rooms
Parapet Work in RO, UPS & gas rooms
Internal plaster and related works
|  | WK 22 (29 - 3) | General electrical final fix |  |  |  |  | Medical gas installation
|  |  | HVAC installation |  |  |  |  | Eleveator Support fixation
|  |  | Final painting |  |  |  |  | External plaster and related works
|  |  | Reception counter and kitchen cabinets |  |  |  |  | Internal plaster and related works
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Refurbish conduit, cables & sockets
|  |  | Installation of medical and non-medical equipment installations. |  |  |  |  | Checking integrity, installation and refurbishing of HVAC works
Block work and internal partitions
Cement, sand and water profing
Doors subframes installation
Column & beams, backfiling & compacting for RO, UPS & gas rooms
Blockworks and Internal Partition Boards for RO,UPS & gas rooms
Doors & windows for RO, UPS & gas rooms
Stairs Ballustrades and Handrailling for RO, UPS & gas rooms
MEPF second and final fixes for RO, UPS & gas rooms
Roof floor finishing for RO, UPS & gas rooms
| JUNE | WK 23 (5 - 10) | General electrical final fix |  |  |  |  | Medical gas installation |  |  | 10 | 77
|  |  | Final painting |  |  |  |  | Eleveator Support fixation
|  |  | Reception counter and kitchen cabinets |  |  |  |  | External plaster and related works
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Internal plaster and related works
|  |  | Installation of medical and non-medical equipment installations. |  |  |  |  | Install new TPs and panel
Refurbish conduit, cables & sockets
Checking integrity, installation and refurbishing of HVAC works
Block work and internal partitions
Cement, sand and water profing
Doors subframes installation
Column & beams, backfiling & compacting for RO, UPS & gas rooms
Internal & External Plaster and related works for RO, UPS & Gas rooms
General MEPF first fix for RO, UPS & gas rooms
Doors & windows for RO, UPS & gas rooms
MEPF second and final fixes for RO, UPS & gas rooms
Roof floor finishing for RO, UPS & gas rooms
|  | WK 24 (12 - 17) | General electrical final fix |  |  |  |  | Medical gas installation
|  |  | Final painting |  |  |  |  | Eleveator Support fixation
|  |  | Reception counter and kitchen cabinets |  |  |  |  | External plaster and related works
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Internal plaster and related works
|  |  | Installation of medical and non-medical equipment installations. |  |  |  |  | Wall screeding and primer painting
Install new cables trays
Install new TPs and panel
Refurbish conduit, cables & sockets
Checking integrity, installation and refurbishing of HVAC works
Block work and internal partitions
Cement, sand and water profing
Doors subframes installation
Internal & External Plaster and related works for RO, UPS & Gas rooms
General MEPF first fix for RO, UPS & gas rooms
Doors & windows for RO, UPS & gas rooms
MEPF second and final fixes for RO, UPS & gas rooms
Roof floor finishing for RO, UPS & gas rooms
External Plaster and related works for RO, UPS & Gas rooms
|  | WK 25 (19 - 24) | General electrical final fix |  |  |  |  | External plaster and related works
|  |  | Final painting |  |  |  |  | Internal plaster and related works
|  |  | Reception counter and kitchen cabinets |  |  |  |  | Wall screeding and primer painting
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Install new cables trays
|  |  | Installation of medical and non-medical equipment installations. |  |  |  |  | Install new TPs and panel
Refurbish conduit, cables & sockets
Checking integrity, installation and refurbishing of HVAC works
Block work and internal partitions
Cement, sand and water profing
Doors subframes installation
General MEPF first fix for RO, UPS & gas rooms
Doors & windows for RO, UPS & gas rooms
Wall screeding & primer painting for RO, UPS & gas rooms
MEPF second and final fixes for RO, UPS & gas rooms
Roof floor finishing for RO, UPS & gas rooms
|  | WK 26 (26 - 1) | General electrical final fix |  |  |  |  | External plaster and related works
|  |  | Final painting |  |  |  |  | Internal plaster and related works
|  |  | Reception counter and kitchen cabinets |  |  |  |  | Wall screeding and primer painting
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Install new cables trays
|  |  | Installation of medical and non-medical equipment installations. |  |  |  |  | Install new TPs and panel
Refurbish conduit, cables & sockets
Checking integrity, installation and refurbishing of HVAC works
Cement, sand and water profing
Doors subframes installation
Doors & windows for RO, UPS & gas rooms
Ceramic Floor Tiling works for UPS, RO & gas rooms
Suspended ceilings for RO, UPS & Gas rooms
Wall screeding & primer painting for RO, UPS & gas rooms
MEPF second and final fixes for RO, UPS & gas rooms
QTR 3 | JULY | WK 27 (3-8) | General electrical final fix |  |  |  |  | External plaster and related works |  |  | 10 | 87 |  |  | 66
|  |  | Final painting |  |  |  |  | Suspended ceiling works
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Furnishing, vanity & closet
|  |  | Installation of medical and non-medical equipment installations. |  |  |  |  | Wall screeding and primer painting
Install new cables trays
Install new TPs and panel
Checking integrity, installation and refurbishing of HVAC works
Internal plaster and related works
Cement, sand and water profing
Doors subframes installation
Site Clearings & External Mechanical pipings & drainages Excavations
Construction of mechanical Manholes
Drainages piping works
Trench Excavations & Electrical Pipe laying
Ceramic Floor Tiling works for UPS, RO & gas rooms
Suspended ceilings for RO, UPS & Gas rooms
MEPF second and final fixes for RO, UPS & gas rooms
Wall screeding & primer painting for RO, UPS & gas rooms
|  | WK 28 (10-15) | General electrical final fix |  |  |  |  | External plaster and related works
|  |  | Final painting |  |  |  |  | Ceramic floor tiling
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Suspended ceiling works
|  |  | Installation of medical and non-medical equipment installations. |  |  |  |  | Furnishing, vanity & closet
Wall screeding and primer painting
Install new cables & trays
Checking integrity, installation and refurbishing of HVAC works
Internal plaster and related works
Doors subframes installation
Site Clearings & External Mechanical pipings & drainages Excavations
Construction of mechanical Manholes
Drainages piping works
Trench Excavations & Electrical Pipe laying
Construction of Electrical Manholes & Trenches with covers
Ceramic Floor Tiling works for UPS, RO & gas rooms
1st & 2nd Coat Paintings for UPS, RO & gas rooms
Wall final painting for UPS, RO & gas rooms
MEPF second and final fixes for RO, UPS & gas rooms
|  | WK 29 (17-22) | General electrical final fix |  |  |  |  | Elevator equipment installation works
|  |  | Final painting |  |  |  |  | Aluminium windows & related works
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Ceramic floor tiling
|  |  | Installation of medical and non-medical equipment installations. |  |  |  |  | Ceramic wall tiling
Suspended ceiling works
Furnishing, vanity & closet
Install water supply fixtures
Wall sockets, switches & lighting fixtures
Refurbish existing firefighting pipes and accessories
Checking integrity, installation and refurbishing of HVAC works
External plaster and related works
Internal plaster and related works
Wall screeding and primer painting
Install new cables & trays
Site Clearings & External Mechanical pipings & drainages Excavations
Construction of mechanical Manholes
Construction of Septic Tank & soak away
Drainages piping works
Trench Excavations & Electrical Pipe laying
Construction of Electrical Manholes & Trenches with covers
1st & 2nd Coat Paintings for UPS, RO & gas rooms
Wall final painting for UPS, RO & gas rooms
MEPF second and final fixes for RO, UPS & gas rooms
|  | WK 30 (24-29) | General electrical final fix |  |  |  |  | Aluminium windows & related works
|  |  | Final painting |  |  |  |  | Steel & wooden doors with related works
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Ceramic floor tiling
|  |  | Installation of medical and non-medical equipment installations. |  |  |  |  | Ceramic wall tiling
Suspended ceiling works
Counter top and cabinet
Sanitary fixtures
Install water supply fixtures
Wall sockets, switches & lighting fixtures
Install firefighting accessories
Refurbish existing firefighting pipes and accessories
Checking integrity, installation and refurbishing of HVAC works
External plaster and related works
Internal plaster and related works
Site Clearings & External Mechanical pipings & drainages Excavations
Construction of mechanical Manholes
Construction of Septic Tank & soak away
Drainages piping works
Trench Excavations & Electrical Pipe laying
Construction of Electrical Manholes & Trenches with covers
Wall final painting for UPS, RO & gas rooms
|  | WK 31 (31-5) | General electrical final fix |  |  |  |  | Stairs, ballustrades & handrailings
|  |  | Final painting |  |  |  |  | Aluminium windows & related works
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Steel & wooden doors with related works
|  |  | Installation of medical and non-medical equipment |  |  |  |  | Ceramic floor tiling
Ceramic wall tiling
Suspended ceiling works
Counter top and cabinet
Sanitary fixtures
Install water supply fixtures
Wall sockets, switches & lighting fixtures
Install firefighting accessories
Checking integrity, installation and refurbishing of HVAC works
Installation of medical and non-medical equipment
External plaster and related works
Internal plaster and related works
Construction of mechanical Manholes
Installation of Water storage Tanks
Construction of Septic Tank & soak away
Drainages piping works
Construction of Electrical Manholes & Trenches with covers
Refurbish existing firefighting pipes and accessories
| AUGUST | WK 32 (7-12) | General electrical final fix |  |  |  |  | Elevator equipment installation works |  |  | 9 | 96
|  |  | Final painting |  |  |  |  | Stairs, ballustrades & handrailings
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Steel & wooden doors with related works
|  |  | Installation of medical and non-medical equipment installations. |  |  |  |  | Ceramic floor tiling
Ceramic wall tiling
Suspended ceiling works
Counter top and cabinet
Sanitary fixtures
Install water supply fixtures
Wall sockets, switches & lighting fixtures
Install firefighting accessories
Checking integrity, installation and refurbishing of HVAC works
Installation of medical and non-medical equipment
External plaster and related works
Installation of Water storage Tanks
Pipe laying works
Construction of Septic Tank & soak away
Refurbish existing firefighting pipes and accessories
|  | WK 33 (14-19) | General electrical final fix |  |  |  |  | Stairs, ballustrades & handrailings
|  |  | Final painting |  |  |  |  | Ceramic floor tiling
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Ceramic wall tiling
|  |  | Installation of medical and non-medical equipment installations. |  |  |  |  | Suspended ceiling works
Wall final painting
Sanitary fixtures
Install water supply fixtures
Wall sockets, switches & lighting fixtures
Install firefighting accessories
Refurbish existing firefighting pipes and accessories
Checking integrity, installation and refurbishing of HVAC works
Installation of medical and non-medical equipment
External plaster and related works
Bore Hole
Installation of Water storage Tanks
Pipe laying works
|  | WK 34 (21-26) | General electrical final fix |  |  |  |  | Stairs, ballustrades & handrailings
|  |  | Final painting |  |  |  |  | Ceramic floor tiling
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Ceramic wall tiling
|  |  | Installation of medical and non-medical equipment installations. |  |  |  |  | Wall final painting
Sanitary fixtures
Install water supply fixtures
Install firefighting accessories
Refurbish existing firefighting pipes and accessories
Installation of medical and non-medical equipment
Bore Hole
Installation of Water storage Tanks
Pipe laying works
|  | WK 35 (28-2) | General electrical final fix |  |  |  |  | Stairs, ballustrades & handrailings
|  |  | Final painting |  |  |  |  | Ceramic wall tiling
|  |  | Procurement of medical and non-medical equipments |  |  |  |  | Wall final painting
|  |  | Installation of medical and non-medical equipment installations. |  |  |  |  | Installation of Water storage Tanks
nstallation of waterpumps
Pipe laying works
Installation of Water Treatment Plant
Installation of Electrical Services panel board connection
MV Cable laying works
Sanitary fixtures
Install firefighting accessories
| SEPTEMBER | WK 36 (4-9) | [5 empty] | Installation of medical and non-medical equipment |  |  | 1.5 | 97.5
Installation of Water storage Tanks
nstallation of waterpumps
Pipe laying works
Installation of Water Treatment Plant
Installation of Electrical Services panel board connection
MV Cable laying works
|  | WK 37 (11-16) | [5 empty] | Installation of medical and non-medical equipment
nstallation of waterpumps
Pipe laying works
Installation of Water Treatment Plant
Installation of Electrical Services panel board connection
MV Cable laying works
|  | WK 38 (18-23) | [5 empty] | Installation of medical and non-medical equipment
Installation of Water Treatment Plant
Installation of Generator
MV Cable laying works
|  | WK 39 (25-30) | [5 empty] | Installation of medical and non-medical equipment
Installation of Generator
QTR4 | OCTOBER | WK 40 (2 - 7) | [5 empty] | Medical and non-medical Equipment installation. |  |  | 1.5 | 99
Installation of Generator
|  | WK 41(9-14) | [5 empty] | Medical and non-medical Equipment installation.
|  | WK 42 (16-21) | [5 empty] | Medical and non-medical Equipment installation.
|  | WK 43 (23-28) | [5 empty] | Medical and non-medical Equipment installation.
| NOVEMBER | WK 44 (30-4) | [5 empty] | Medical and non-medical Equipment installation. |  |  | 1 | 100
Training of personnel
|  | WK 45 (6-11) | [5 empty] | Medical and non-medical Equipment installation.
Training of personnel
|  | WK 46 (13-18) | [5 empty] | Medical and non-medical Equipment installation.
Training of personnel
Testing
|  | WK 47 (20-25) | [5 empty] | Training of personnel
Testing
|  | WK 48 (27-2) | [5 empty] | Commissioning and handing over
50%
45%
100%
[14 empty] | Month | 2022 | Jan | Feb | Mar |  | Apr | May | June | July | Aug | Sept | Oct | Nov
[13 empty] | OPD + IPD | Monthly |  | 4% | 3% | 10% |  | 16% | 16% | 10% | 10% | 9% | 1.5% | 1.5% | 1%
[14 empty] | Cummilative | 18% | 22% | 25% | 35% |  | 51% | 67% | 77% | 87% | 96% | 97.5% | 99% | 100%
[13 empty] | OPD | Monthly
[14 empty] | Cummilative | 35% | 43% | 48% | 53% |  | 69% | 88% | 94% | 97% | 100%
[13 empty] | IPD | Monthly | [9 empty] | 96% | 97.5% | 99% | 100%
[14 empty] | Cummilative | 0% | 0% | 1% | 17% |  | 31% | 46% | 58% | 75% | 92% | 97% | 98.5% | 100%
[11 empty] | OPD +IPD | [7 empty] | OPD
IPD