## Slide 1
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
STELLA OBASANJO HOSPITAL Edo state ministry of Health
PROGRESS REPORT: WEEK 6
CIVIL WORKS IN 0PD BLOCK
CIVIL WORKS IN IPD BLOCK
MEDICAL EQUIPMENT AND FURNITURE
NEXT STAGE
EQUIPMENT PROCESS FLOW

## Slide 2: Civil works in OPD block
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
Phase
Chart: 
| 2022 | Jan | Feb | Mar | Apr | May | June | July | Aug
 | 0.35 | 0.43 | 0.48 | 0.53 | 0.69 | 0.88 | 0.94 | 0.97 | 1
% PERCENTAGE COMPLETION
09, February 2023
44.5%
ONGOING ACTIVITIES
Plastering of internal and external walls
MEPF first fix
Casting of parapet wall

## Slide 3: Civil works in IPD block
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
% PERCENTAGE COMPLETION
09, February 2023
0%
Chart: 
| 2022 | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov
 | 0 | 0 | 0.01 | 0.17 | 0.31 | 0.46 | 0.58 | 0.75 | 0.92 | 0.97 | 0.985 | 1
ONGOING ACTIVITIES
NIL

## Slide 4: Disbursement
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
ACTIVITY | STATUS
OPD CIVIL WORKS | Honoring of interim valuation certificate
IPD CIVIL WORKS | Contractor awaiting mobilization
MEDICAL & NON-MEDICAL EQUIPMENTS | Invoices received from vendors. Vendors awaiting mobilization

## Slide 5: Procurement, Storage, & Logistic plans for SOH medical equipment & furniture
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
Reception
Storage
DELIVERY
Supply schedule
BOQ
Equipment tag
Room tag
ISSUANCE
EXIT
Personnel
Methodology
Timing
Security
Space improvement
Burglary
Locks
A/C installation
Fire extinguisher
Submission of invoices
Payment
PRE-ENTRY
ENTRY
Order
INSTALLATION & TESTING
Training
Hand over
CLOSE-OUT
TANIT
MOH
CONTRACTOR
TANIT
CONTRACTOR
TANIT
MOH
CONTRACTOR
TANIT
MOH
CONTRACTOR
TANIT
CONTRACTOR
TANIT
MOH
CONTRACTOR
CURRENT
STATE
Current state & current level
Yet to commence
Periodic updates