## Slide 1
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
STELLA OBASANJO HOSPITAL Edo state ministry of Health
PROGRESS REPORT: WEEK 7
(13th – 18th February 2023)
CIVIL WORKS IN 0PD BLOCK
CIVIL WORKS IN IPD BLOCK
PROJECT WEEKLY ACTIVITIES
FINANCIAL DETAILS
PICTURE EXCERPTS

## Slide 2: Civil works in OPD block
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
Phase
Chart: 
| 2022 | Jan | Feb | Mar | Apr | May | June | July | Aug
 | 0.35 | 0.43 | 0.48 | 0.53 | 0.69 | 0.88 | 0.94 | 0.97 | 1
% PERCENTAGE COMPLETION
14, February 2023
45.8%
ONGOING WEEK 7 ACTIVITIES

## Slide 3: Civil works in IPD block
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
% PERCENTAGE COMPLETION
09, February 2023
0.75%
Chart: 
| 2022 | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov
 | 0 | 0 | 0.01 | 0.17 | 0.31 | 0.46 | 0.58 | 0.75 | 0.92 | 0.97 | 0.985 | 1
ONGOING ACTIVITIES
NIL
PREVIOUS ACTIVITIES IN IPD
Removal of suspended ceiling
Removal of sanitary wares
Removal Air-conditioners
All item carefully accounted for and stored in container on site

## Slide 4: Project weekly activities
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
WEEK 7: 13th – 18th February, 2023
TASK/ACTIVITY |  |  |  | % EXPECTED CUMULATIVE TARGET (OPD & IPD)
OPD |  | IPD |  | 
Activity | % Expected Cumulative weekly target | Activity | % Expected Cumulative weekly target | 
Internal & External plastering works | 46.75 | Financial options payment and cash flow plan being processed | 0.75 | 24.25
General MEPF first fix |  |  |  | 
Block work in hydrotherapy pool pump house |  |  |  | 
Primer painting |  |  |  | 
In view : WEEK 8
TASK/ACTIVITY |  |  |  | % EXPECTED CUMULATIVE TARGET (OPD & IPD)
OPD |  | IPD |  | 
Activity | % Expected Cumulative weekly target | Activity | % Expected Cumulative weekly target | 
Internal & External plastering works | 48 | Financial options payment and cash flow plan being processed | 1 | 
General MEPF first fix |  |  |  | 
Block work in hydrotherapy pool pump house |  |  |  | 
Primer painting |  |  |  | 

## Slide 5: Financial Details
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
ACTIVITY | STATUS
OPD CIVIL WORKS | Interim valuation certificate for OPD Civil works currently been processed by MOH
IPD CIVIL WORKS | Contractor awaiting mobilization
MEDICAL & NON-MEDICAL EQUIPMENTS | Invoices received from vendors. Financial options payment and cash flow plan being processed Vendors awaiting mobilization

## Slide 6: Picture excerpts
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
Electrical piping works in OPD
Perspective view of external plaster works in OPD

## Slide 7: Picture excerpts
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
Primer painting works in OPD
Hydrotherapy pull pump house

## Slide 8: Picture excerpts
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
Front view perspective of IPD
Careful removal of suspended ceiling in IPD

## Slide 9: End of presentation
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
Thank you for your time.
From all of us at
TANIT MEDICAL ENGINEERING
Let love lead