•     CIVIL  WORKS  IN 0PD BLOCK

•     CIVIL  WORKS  IN /PD BLOCK

•    PAYMENT PLAN SCHEDULE

STELLA

OBASANJO HOSPITAL

Edo state ministry of Health

PROGRESS REPORT: WEEK 7 (13th - 18th  February 2023)

TANIT MEDICAL ENGINEERING                                                                                                                                                       February 2023

Civil works in OPD block

% PERCENTAGE COMPLETION

14, February 2023

45.8%

110%

100%

90%

80%

70%

60%

. ...       I

I

94%

100%

ONGOING  WEEK 7 ACTIVITIES

Plastering of internal & external walls  [                     70%           50%

II

Casting of parapet wall                            I                                           100%            40%         35%

MEPF first fix                                         [                 61.1%                  30% Primer painting                      I  12.90%           20% Hydrotherapy pool pump house wall      I         5%                           10%

0%

53%                                  II

II

II

II

II

II

II II

II

2022                            Jan          Feb          Mar                        Apr        May        June                        July         Aug

TANIT MEDICAL ENGINEERING                                                                                                                                                    February 2023

Civil works in  IPD  block

% PERCENTAGE COMPLETION

14, February 2023

110%

100%

90%

0.75%                                                                  92%

ONGOING ACTIVITIES

•    NIL

80%

70%

60%

50%

40%

75%

PREVIOUS ACTIVITIES IN IPD

•     Removal of suspended ceiling

•     Removal of sanitary wares

•     Removal Air-conditioners

All item carefully accounted for and stored in container on site

30%

20%

10%

0%

0%

2022

0%

Jan        Feb       Mar                    Apr      May     June                   July      Aug     Sept                 Oct       Nov

TANIT MEDICAL ENGINEERING                                                                                                                                                    February 2023

Contractors Payment Plan Schedule

Contractors                                                                               Payment plan

•  Sudabelt Medical  Equipment limited

LOT1  (MEDICAL EQUIPMENT)

N1,625,778,150.00

•  Sudabelt Medical  Equipment limited  LOT2  (RADIOLOGY) N2,104,552,000.00

1. 50% mobilization  payment on all  3 LOTs

2. 20% Advance payment after 30days for LOT1 & LOTS

3. 20% Advance payment after 60 days from  date of first mobilization for

LOT2

4. 20% Advance payment after 4 months from initial  mobilization for LOT1 &

LOTS

•  Sudabelt Medical  Equipment limited

LOTS (IVF & LAB)

N1,090,041,596.00

5. 10% Advance payment after 5 months from initial  payment for LOT1 & LOTS  upon completion of installation  and 20% for LOT2 upon provision of packing list and associated  shipping  documents from  OEM.

6. Balance  payment of 10% after 6 months from  initial  payment upon delivery and installation  of LOT2

TANIT MEDICAL ENGINEERING                                                                                                                                                    February 2023

Contractors Payment Plan Schedule

Contractors                                                                               Payment plan

1. 60% mobilization  payment on LOT3

•  Supreme  Meditech

LOT3  Medical

{MEDICAL GASES) N648,989,222.31

2. 20% Advance payment after 30 days

3.15% Advance payment after 4 months from  mobilization

4. Balance  payment of 5% upon delivery for LOT3 after 7 months from  initial payment

1. 50% mobilization  on LOT3

•  BlueHub

LOT3  Non-medical

{IT & APPLIANCES) N105,440,181.75

2. 30% Advance payment, 4 months after mobilization  upon delivery and inspection of goods in the warehouse

3. Balance  payment of 20%, 6 months from  initial  mobilization subject to completion of installation

TANIT MEDICAL ENGINEERING                                                                                                                                                    February 2023

Contractors Payment Plan Schedule

Contractors                                                                               Payment plan

1. 60% mobilization

•		Reedpriceman LOT2  Non-medical (OFFICE  FURNITURE) N409,710,761.75

2. 20% Advance payment after 60 days from  initial  mobilization, and upon inspection  of goods in the warehouse

3. Balance  payment of 20% upon installation  after 4 months from  initial mobilization

•  Sabtrak Limited

LOT  1 Non-medical (OFFICE APPLIANCE) N14,850,609.00

1. 10% mobilization

2. 60% advance payment after 4 months from  mobilization, and upon inspection  of goods in the warehouse  and delivery to site.

3. Balance  payment of 30% upon installation, 5 months after mobilization.

TANIT MEDICAL ENGINEERING                                                                                                                                                    February 2023

Contractors  Payment  Plan Schedule

LOT

Number        Description                     Supplier

30•        01•

Month           15-Feb-23          15-Mar-23                 30-Apr-23    May-23    Jun-23               01-Jul-23            01-Aug-23               01-Sep-23            01-Oct-23   LOT TOTALS  PHASE 1

MEDICAL EQUIPMENT    SUDABELT MEDICAL                                                                                                                          162,577,815.0

LOT1                                          COMPANYLTD               812,889,075.00     325,155,630.00                       -       -                   -                  325,155,630.00   0                                                         -      -                                           1,625,778,150.00

RADIOLOGY                         SUDABELT MEDICAL         1,052,276,000.0                                                                                                420,910,400.0

LOT2                                          COMPANYLTD               0                                                        -          420,910,400.00    -                      -                     -                                         0                          210,455,200.00    -                                             2,104,552,000.00

LABORATORY & IVF       SUDABELT MEDICAL                                                                                                                          109,004,159.6

LOTS                                          COMPANYLTD               545,020,798.00     218,008,319.20                       -       -                   -                  218,008,319.20   0                                                         -      -                                           1,090,041,596.00

MEDICAL GASES AND         SUPREME MEDITECH

LOT3          PLANT                                   LTD                             389,393,533.39     129,797,844.46                       -       -                   -                  97,348,383.35        -                                                                 -     32,449,461.12                648,989,222.31

LOT6

I1./ AUDIOVISUAL

(PART)                                         BLUEHUBLTD                         52,720,090.88                        -                                     -       -                   -                  31,632,054.53        -                                      21,088,036.35     -                                             105,440,181.75

LOT6

(PART) LOT6

FURNITURE

APPLIANCES

| 81,942,152.35 | - - 81,942,152.35 | - | - | - | 409,710,761.75 |
| --- | --- | --- | --- | --- | --- |

REED PRICEMAN LTD        245,826,457.05                               .

(PART)                                         SABTRAKLTD                 1,485,060.90                          -                                    -       -                   -                      8,910,365.40      -                                 4,455,182.70           -                                               14,850,609.00

.

MONTHLYTOTALS              3,099,611,015.21      672,961,793.66         502,852,552.35       .                .                 762,996,904.82      692,492,374.60        235,998,419.05       32,449,461.12         5,999,362,520.81

TANIT MEDICAL ENGINEERING                                                                                                                                                    February 2023