## Slide 1
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
STELLA OBASANJO HOSPITAL Edo state ministry of Health
PROGRESS REPORT: WEEK 7
(13th – 18th February 2023)
CIVIL WORKS IN 0PD BLOCK
CIVIL WORKS IN IPD BLOCK
PAYMENT PLAN SCHEDULE

## Slide 2: Civil works in OPD block
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
Phase
Chart: 
| 2022 | Jan | Feb | Mar | Apr | May | June | July | Aug
 | 0.35 | 0.43 | 0.48 | 0.53 | 0.69 | 0.88 | 0.94 | 0.97 | 1
% PERCENTAGE COMPLETION
14, February 2023
45.8%
ONGOING WEEK 7 ACTIVITIES

## Slide 3: Civil works in IPD block
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
% PERCENTAGE COMPLETION
14, February 2023
0.75%
Chart: 
| 2022 | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov
 | 0 | 0 | 0.01 | 0.17 | 0.31 | 0.46 | 0.58 | 0.75 | 0.92 | 0.97 | 0.985 | 1
ONGOING ACTIVITIES
NIL
PREVIOUS ACTIVITIES IN IPD
Removal of suspended ceiling
Removal of sanitary wares
Removal Air-conditioners
All item carefully accounted for and stored in container on site

## Slide 4: Contractors Payment Plan Schedule
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
Contractors | Payment plan
Sudabelt Medical Equipment limited LOT1 (MEDICAL EQUIPMENT) ₦1,625,778,150.00 | 50% mobilization payment on all 3 LOTs 20% Advance payment after 30days for LOT1 & LOT5 20% Advance payment after 60 days from date of first mobilization for LOT2 20% Advance payment after 4 months from initial mobilization for LOT1 & LOT5 10% Advance payment after 5 months from initial payment for LOT1 & LOT5 upon completion of installation and 20% for LOT2 upon provision of packing list and associated shipping documents from OEM. Balance payment of 10% after 6 months from initial payment upon delivery and installation of LOT2
Sudabelt Medical Equipment limited LOT2 (RADIOLOGY) ₦2,104,552,000.00 | 
Sudabelt Medical Equipment limited LOT5 (IVF & LAB) ₦1,090,041,596.00 | 

## Slide 5: Contractors Payment Plan Schedule
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
Contractors | Payment plan
Supreme Meditech LOT3 Medical (MEDICAL GASES) ₦648,989,222.31 | 60% mobilization payment on LOT3 20% Advance payment after 30 days 15% Advance payment after 4 months from mobilization Balance payment of 5% upon delivery for LOT3 after 7 months from initial payment
BlueHub LOT3 Non-medical (IT & APPLIANCES) ₦105,440,181.75 | 50% mobilization on LOT3 30% Advance payment, 4 months after mobilization upon delivery and inspection of goods in the warehouse Balance payment of 20%, 6 months from initial mobilization subject to completion of installation

## Slide 6: Contractors Payment Plan Schedule
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023
Contractors | Payment plan
Reedpriceman LOT2 Non-medical (OFFICE FURNITURE) ₦409,710,761.75 | 60% mobilization 20% Advance payment after 60 days from initial mobilization, and upon inspection of goods in the warehouse Balance payment of 20% upon installation after 4 months from initial mobilization
Sabtrak Limited LOT 1 Non-medical (OFFICE APPLIANCE) ₦14,850,609.00 | 10% mobilization 60% advance payment after 4 months from mobilization, and upon inspection of goods in the warehouse and delivery to site. Balance payment of 30% upon installation, 5 months after mobilization.

## Slide 7: Contractors Payment Plan Schedule
TANIT MEDICAL ENGINEERING
TANIT MEDICAL ENGINEERING February 2023