## SOH PHASE PLANNING TEMPLATE 1
STELLA OBASANJO HOSPITAL PHASE PLANNING
|  |  | FULL PROJECT 9-12 MONTHS | Option 1 (9-12 months)
|  | Description | FULL PROJECT WITH ADMIN | Full Project LESS ADMIN
S/No. | CONTRACTOR | ITEMS
1 | A & K Construction Limited | OPD - Out Patient Department | 1176578029.99 | 1176578029.99
2 | A & K Construction Limited | IPD - In Patient Department | 3129724081.1 | 3129724081.1
3 | A & K Construction Limited | Administrative Block | 2400786761.68 | 0
4 | TO BE ADVISED - TBA | Mortuary (Estimate) | 250000000 | 250000000
|  | SUB TOTAL - CONSTRUCTION | 6957088872.77 | 4556302111.09
|  | Expected Construction Variation @10% | 695708887.277 | 455630211.109
|  | Construction Total | 7652797760.047 | 5011932322.199
1 | SUDABELT MEDICAL CO. LTD | Lot 1 - Medical Equipment | 4135198000 | 4135198000
2 | SUDABELT MEDICAL CO. LTD | Lot 2 - Radiology | 2104552000 | 2104552000
3 | SUPREME MEDITECH LTD. | Lot 3 - Medical Gases | 648989222.31 | 648989222.31
4 | SUPREME MEDITECH LTD. | Lot 4 - Mortuary | 129241980 | 129241980
5 | SUDABELT MEDICAL CO. LTD | Lot 5 - Laboratory | 1090041596 | 1090041596
6 | REEDPRICEMAN | KITCHEN LAUNDRY TOOLS + FURNITURE | 339472422.5 | 339472422.5
7 | BLUEHUB LTD | IT EQUIPMENT AND AUDIOVISUALS | 357722837.25 | 134105239.5
8 | SABTRAK LTD | APPLIANCES | 42407202 | 35573814
9 | REEDPRICEMAN | OFFICE FURNITURE | 1492211413 | 809369069.5
|  | EQUIPMENT AND FURNISHING SUB TOTAL | 10339836673.06 | 9426543343.81
|  | Expected Equipment & Furnishing Variation@10% | 1033983667.306 | 471327167.1905
|  | TOTAL EQUIPMENT AND FURNISHING COST | 11373820340.366 | 9897870511.0005
|  | SCENARIO TOTAL SUM | 19026618100.413 | 14909802833.1995
|  |  | DIFFERENCE | 4116815267.2135
EQUIPMENT PAYMENT PLAN
|  | Initial Payment (15 days) 50% | 5686910170.183 | 4948935255.5002
|  | Next Payment (60 days) 30% | 3412146102.1098 | 2969361153.3001
|  | Final Payment (Post Deployment) 20% | 2274764068.0732 | 1979574102.2001
This is excludes all Preoperational cost
APPROXIMATE ESTIMATED COST OF MORTUARY
Total floor area of OPD IS 2,458
Total contract sum of OPD IS 1,176,578,029.99
Cost per m2 cost/are= N478,672.92
| TOTAL FLOOR AREA OF MORTUARY SHOULD BE NO MORE THAN 550 M2 |  | TO BE REDESIGNED
Utilizing average cost Per Sq. metre of N445,545.00
This gives - N454,545.00 x 550 = N 250,000,000.00
Cost of constructing mortuary is N 250,000,000 - Estimated