## SOH PHASE PLANNING TEMPLATE 1
STELLA OBASANJO HOSPITAL PHASE PLANNING
|  |  | FULL PROJECT 9-12 MONTHS | Option 1 (9-12 months) | Option 2 (6-9 Months) | Option 3 (6-9 Months) | Option 4 (6-7 Months)
|  | Description | FULL PROJECT WITH ADMIN | Full Project LESS ADMIN | OPD + DIAG/DIALYSIS/IVF/ER + MORTUARY + MEDICAL GASES | OPD + DIAG/DIALYSIS/IVF/ER + MEDICAL GASES | OPD + DIAG/DIALYSIS/IVF/ER
S/No. | CONTRACTOR | ITEMS
1 | A & K Construction Limited | OPD - Out Patient Department | 1176578029.99 | 1176578029.99 | 1176578029.99 | 1176578029.99 | 1176578029.99
2 | A & K Construction Limited | IPD - In Patient Department | 3129724081.1 | 3129724081.1 | 1877834448.66 | 1564862040.55 | 1564862040.55
3 | A & K Construction Limited | Administrative Block | 2400786761.68 | 0 | 0 | 0 | 0
4 | TO BE ADVISED - TBA | Mortuary (Estimate) | 250000000 | 250000000 | 250000000 | 0 | 0
|  | SUB TOTAL - CONSTRUCTION | 6957088872.77 | 4556302111.09 | 3304412478.65 | 2741440070.54 | 2741440070.54
|  | Expected Construction Variation @10% | 695708887.277 | 455630211.109 | 330441247.865 | 274144007.054 | 274144007.054
|  | Construction Total | 7652797760.047 | 5011932322.199 | 3634853726.515 | 3015584077.594 | 3015584077.594
1 | SUDABELT MEDICAL CO. LTD | Lot 1 - Medical Equipment | 4135198000 | 4135198000 | 1566785650 | 1566785650 | 1566785650
2 | SUDABELT MEDICAL CO. LTD | Lot 2 - Radiology | 2104552000 | 2104552000 | 2104552000 | 2104552000 | 2104552000
3 | SUPREME MEDITECH LTD. | Lot 3 - Medical Gases | 648989222.31 | 648989222.31 | 648989222.31 | 648989222.31 | 0
4 | SUPREME MEDITECH LTD. | Lot 4 - Mortuary | 129241980 | 129241980 | 129241980 | 0 | 0
5 | SUDABELT MEDICAL CO. LTD | Lot 5 - Laboratory | 1090041596 | 1090041596 | 1090041596 | 1090041596 | 1090041596
6 | REEDPRICEMAN | KITCHEN LAUNDRY TOOLS + FURNITURE | 339472422.5 | 339472422.5 | 0 | 0 | 0
7 | BLUEHUB LTD | IT EQUIPMENT AND AUDIOVISUALS | 357722837.25 | 134105239.5 | 83156302.5 | 83156302.5 | 83156302.5
8 | SABTRAK LTD | APPLIANCES | 42407202 | 37872852 | 13169223 | 13169223 | 13169223
9 | REEDPRICEMAN | OFFICE FURNITURE | 1492211413 | 802346094.5 | 422083323.75 | 422083323.75 | 422083323.75
|  | EQUIPMENT AND FURNISHING SUB TOTAL | 10339836673.06 | 9421819406.81 | 6058019297.56 | 5928777317.56 | 5279788095.25
|  | Expected Equipment & Furnishing Variation@10% | 1033983667.306 | 471090970.3405 | 605801929.756 | 592877731.756 | 527978809.525
|  | TOTAL EQUIPMENT AND FURNISHING COST | 11373820340.366 | 9892910377.1505 | 6663821227.316 | 6521655049.316 | 5807766904.775
|  | SCENARIO TOTAL SUM | 19026618100.413 | 14904842699.3495 | 10298674953.831 | 9537239126.91 | 8823350982.369
|  |  | DIFFERENCE | 4121775401.0635 | 8727943146.582 | 9489378973.503 | 10203267118.044
EQUIPMENT PAYMENT PLAN
|  | Initial Payment (15 days) 50% | 5686910170.183 | 4946455188.5752 | 3331910613.658 | 3260827524.658 | 2903883452.3875
|  | Next Payment (60 days) 30% | 3412146102.1098 | 2967873113.1451 | 1999146368.1948 | 1956496514.7948 | 1742330071.4325
|  | Final Payment (Post Deployment) 20% | 2274764068.0732 | 1978582075.4301 | 1332764245.4632 | 1304331009.8632 | 1161553380.955
This is excludes all Preoperational cost
APPROXIMATE ESTIMATED COST OF MORTUARY
Total floor area of OPD IS 2,458
Total contract sum of OPD IS 1,176,578,029.99
Cost per m2 cost/are= N478,672.92
| TOTAL FLOOR AREA OF MORTUARY SHOULD BE NO MORE THAN 550 M2 |  | TO BE REDESIGNED
Utilizing average cost Per Sq. metre of N445,545.00
This gives - N454,545.00 x 550 = N 250,000,000.00
Cost of constructing mortuary is N 250,000,000 - Estimated