## SOH PHASE PLANNING TEMPLATE 1
STELLA OBASANJO HOSPITAL PHASE PLANNING
|  |  | FULL PROJECT 9-12 MONTHS | Option 1 (9-12 months) | Option 2 (6-9 Months) | Option 3 (6-9 Months) | Option 4 (6-7 Months)
|  | Description | FULL PROJECT WITH ADMIN | Full Project LESS ADMIN | OPD + DIAG/DIALYSIS/IVF/ER + MORTUARY + MEDICAL GASES | OPD + DIAG/DIALYSIS/IVF/ER + MEDICAL GASES | OPD + DIAG/DIALYSIS/IVF/ER
S/No. | CONTRACTOR | ITEMS
1 | A & K Construction Limited | OPD - Out Patient Department | 1176578029.99 | 1176578029.99 | 1176578029.99 | 1176578029.99 | 1176578029.99
2 | A & K Construction Limited | IPD - In Patient Department | 3129724081.1 | 3129724081.1 | 1877834448.66 | 1564862040.55 | 1564862040.55
3 | A & K Construction Limited | Administrative Block | 2400786761.68 | 0 | 0 | 0 | 0
4 | TO BE ADVISED - TBA | Mortuary (Estimate) | 250000000 | 250000000 | 250000000 | 0 | 0
|  | SUB TOTAL - CONSTRUCTION | 6957088872.77 | 4556302111.09 | 3304412478.65 | 2741440070.54 | 2741440070.54
|  | Expected Construction Variation @10% | 695708887.277 | 455630211.109 | 330441247.865 | 274144007.054 | 274144007.054
|  | Construction Total | 7652797760.047 | 5011932322.199 | 3634853726.515 | 3015584077.594 | 3015584077.594
1 | SUDABELT MEDICAL CO. LTD | Lot 1 - Medical Equipment | 4135198000 | 4135198000 | 1566785650 | 1385962650 | 1566785650 | 1566785650
2 | SUDABELT MEDICAL CO. LTD | Lot 2 - Radiology | 2104552000 | 2104552000 | 2104552000 | 2104552000 | 2104552000
3 | SUPREME MEDITECH LTD. | Lot 3 - Medical Gases | 648989222.31 | 648989222.31 | 648989222.31 | 648989222.31 | 0
4 | SUPREME MEDITECH LTD. | Lot 4 - Mortuary | 129241980 | 129241980 | 129241980 | 0 | 0
5 | SUDABELT MEDICAL CO. LTD | Lot 5 - Laboratory | 1090041596 | 1090041596 | 1090041596 | 803323944 | 1090041596 | 1090041596
6 | REEDPRICEMAN | KITCHEN LAUNDRY TOOLS + FURNITURE | 339472422.5 | 339472422.5 | 0 | 0 | 0
7 | BLUEHUB LTD | IT EQUIPMENT AND AUDIOVISUALS | 357722837.25 | 134105239.5 | 83156302.5 | 83156302.5 | 83156302.5
8 | SABTRAK LTD | APPLIANCES | 42407202 | 35573814 | 10870185 | 10870185 | 10870185
9 | REEDPRICEMAN | OFFICE FURNITURE | 1492211413 | 809369069.5 | 429106298.75 | 429106298.75 | 429106298.75
|  | EQUIPMENT AND FURNISHING SUB TOTAL | 10339836673.06 | 9426543343.81 | 6062743234.56 | 5465960602.56 | 5284512032.25
|  | Expected Equipment & Furnishing Variation@5% | 516991833.653 | 471327167.1905 | 303137161.728 | 273298030.128 | 264225601.6125
|  | TOTAL EQUIPMENT AND FURNISHING COST | 10856828506.713 | 9897870511.0005 | 6365880396.288 | 5739258632.688 | 5548737633.8625
|  | SCENARIO TOTAL SUM | 18509626266.76 | 14909802833.1995 | 10000734122.803 | 8754842710.282 | 8564321711.4565
|  |  | DIFFERENCE | 3599823433.5605 | 8508892143.957 | 9754783556.478 | 9945304555.3035
EQUIPMENT PAYMENT PLAN
|  | Initial Payment (15 days) 80% | 8685462805.3704 | 7918296408.8004 | 5092704317.0304 | 4591406906.1504 | 4438990107.09
|  | Next Payment (60 days) 10% | 1085682850.6713 | 989787051.1 | 636588039.6288 | 573925863.2688 | 554873763.3863
|  | Final Payment (Post Deployment) 10% | 1085682850.6713 | 989787051.1 | 636588039.6288 | 573925863.2688 | 554873763.3863
This is excludes all Preoperational cost
APPROXIMATE ESTIMATED COST OF MORTUARY
Total floor area of OPD IS 2,458
Total contract sum of OPD IS 1,176,578,029.99
Cost per m2 cost/are= N478,672.92
| TOTAL FLOOR AREA OF MORTUARY SHOULD BE NO MORE THAN 550 M2 |  | TO BE REDESIGNED
Utilizing average cost Per Sq. metre of N445,545.00
This gives - N454,545.00 x 550 = N 250,000,000.00
Cost of constructing mortuary is N 250,000,000 - Estimated