## SOH PHASE PLANNING TEMPLATE
STELLA OBASANJO HOSPITAL PHASE PLANNING
|  |  | FULL PROJECT 9-12 MONTHS | QUICK ACTION | Option 1 (9-12 months) | Option 2 (6-9 Months) | Option 3 (6-7 Months)
|  | Description | EASY PAYMENT PLAN |  | Full Project LESS ADMIN | OPD + DIAGNOSTICS + MORTUARY + INFRASTRUCTURE | OPD + DIAG STRIPPED DOWN
S/No. | CONTRACTOR | ITEMS
1 | A & K Construction Limited | OPD - Out Patient Department | 1176578029.99 |  | 1176578029.99 | 1176578029.99 | 1176578029.99
2 | A & K Construction Limited | IPD - In Patient Department | 3129724081.1 |  | 3129724081.1 | 1877834448.66 | 1564862040.55
3 | A & K Construction Limited | Administrative Block | 1664024501.8 |  | 0 | 0 | 0
4 | TO BE ADVISED - TBA | Mortuary (Estimate) | 250000000 |  | 250000000 | 250000000 | 0
|  | SUB TOTAL - CONSTRUCTION | 6220326612.89 | TO NEGOTIATE | 4556302111.09 | 3304412478.65 | 2741440070.54
|  | Construction Variation @10% | 622032661.289 | VARIATION 5% | 227815105.5545 | 165220623.9325 | 137072003.527
|  | Construction Total | 6842359274.179 |  | 4784117216.6445 | 3469633102.5825 | 2878512074.067
1 | SUDABELT MEDICAL CO. LTD | Lot 1 - Medical Equipment | 4135198000 |  | 4135198000 | 2067599000 | 2067599000
2 | SUDABELT MEDICAL CO. LTD | Lot 2 - Radiology | 2104552000 |  | 2104552000 | 2104552000 | 2104552000
3 | SUPREME MEDITECH LTD. | Lot 3 - Medical Gases | 648989222.31 |  | 648989222.31 | 648989222.31 | 0
4 | SUPREME MEDITECH LTD. | Lot 4 - Mortuary | 129241980 |  | 129241980 | 129241980 | 0
5 | SUDABELT MEDICAL CO. LTD | Lot 5 - Laboratory | 1090041596 |  | 1090041596 | 1090041596 | 1090041596
6 | REEDPRICEMAN | KITCHEN LAUNDRY TOOLS + FURNITURE | 339472422.5 |  | 339472422.5 | 0 | 0
7 | BLUEHUB LTD | IT EQUIPMENT AND AUDIOVISUALS | 357722837.25 |  | 143089134.9 | 71544567.45 | 71544567.45
8 | SABTRAK LTD | APPLIANCES | 42407202 |  | 25444321.2 | 12722160.6 | 12722160.6
9 | REEDPRICEMAN | OFFICE FURNITURE | 1492211413 |  | 1044547989.1 | 783410991.825 | 783410991.825
|  | EQUIPMENT AND FURNISHING SUB TOTAL | 10339836673.06 | TO NEGOTIATE | 9660576666.01 | 6908101518.185 | 6129870315.875
|  | Equipment & Furnishing Variation@10% | 1033983667.306 | VARIATION 5% | 483028833.3005 | 345405075.9093 | 306493515.7937
|  | TOTAL EQUIPMENT AND FURNISHING COST | 11373820340.366 |  | 10143605499.3105 | 7253506594.0942 | 6436363831.6687
|  |  | 18216179614.545 |  | 14927722715.955 | 10723139696.6768 | 9314875905.7358
|  |  |  | DIFFERENCE | 3288456898.59 | 7493039917.8682 | 8901303708.8092
EQUIPMENT PAYMENT PLAN
|  | Initial Payment (15 days) 50% | 5686910170.183 |  | 5071802749.6553 | 3626753297.0471 | 3218181915.8344
|  | Next Payment (60 days) 30% | 3412146102.1098 |  | 3043081649.7932 | 2176051978.2283 | 1930909149.5006
|  | Final Payment (Post Deployment) 20% | 2274764068.0732 |  | 2028721099.8621 | 1450701318.8189 | 1287272766.3338
SCENARIO TOTAL SUM
This is excludes all Preoperational cost
APPROXIMATE ESTIMATED COST OF MORTUARY
Total floor area of OPD IS 2,458
Total contract sum of OPD IS 1,176,578,029.99
Cost per m2 cost/are= N478,672.92
| Total floor area for mortuary is 500 M2 |  | TO BE REDESIGNED
Utilizing average cost Per Sq. metre of N400,000
This gives - N400,000 x 500 = N 200,000,000.00
Cost of constructing mortuary is N 250,000,000 - Estimated

## SOH PHASE PLANNING TEMPLATE 1
STELLA OBASANJO HOSPITAL PHASE PLANNING
|  |  | FULL PROJECT 9-12 MONTHS | QUICK ACTION | Option 1 (9-12 months) | Option 2 (6-9 Months) | Option 3 (6-7 Months)
|  | Description | EASY PAYMENT PLAN |  | Full Project LESS ADMIN | OPD + DIAGNOSTICS + MORTUARY + INFRASTRUCTURE | OPD + DIAG STRIPPED DOWN
S/No. | CONTRACTOR | ITEMS
1 | A & K Construction Limited | OPD - Out Patient Department | 1176578029.99 |  | 1176578029.99 | 1176578029.99 | 1176578029.99
2 | A & K Construction Limited | IPD - In Patient Department | 3129724081.1 |  | 3129724081.1 | 1877834448.66 | 1564862040.55
3 | A & K Construction Limited | Administrative Block | 2400786761.68 |  | 0 | 0 | 0
4 | TO BE ADVISED - TBA | Mortuary (Estimate) | 250000000 |  | 250000000 | 250000000 | 0
|  | SUB TOTAL - CONSTRUCTION | 6957088872.77 | TO NEGOTIATE | 4556302111.09 | 3304412478.65 | 2741440070.54
|  | Construction Variation @10% | 695708887.277 | VARIATION 5% | 227815105.5545 | 165220623.9325 | 137072003.527
|  | Construction Total | 7652797760.047 |  | 4784117216.6445 | 3469633102.5825 | 2878512074.067
1 | SUDABELT MEDICAL CO. LTD | Lot 1 - Medical Equipment | 4135198000 |  | 4135198000 | 1566785650 | 1566785650
2 | SUDABELT MEDICAL CO. LTD | Lot 2 - Radiology | 2104552000 |  | 2104552000 | 2104552000 | 2104552000
3 | SUPREME MEDITECH LTD. | Lot 3 - Medical Gases | 648989222.31 |  | 648989222.31 | 648989222.31 | 0
4 | SUPREME MEDITECH LTD. | Lot 4 - Mortuary | 129241980 |  | 129241980 | 129241980 | 0
5 | SUDABELT MEDICAL CO. LTD | Lot 5 - Laboratory | 1090041596 |  | 1090041596 | 1090041596 | 1090041596
6 | REEDPRICEMAN | KITCHEN LAUNDRY TOOLS + FURNITURE | 339472422.5 |  | 339472422.5 | 0 | 0
7 | BLUEHUB LTD | IT EQUIPMENT AND AUDIOVISUALS | 357722837.25 |  | 134105239.5 | 83156302.5 | 83156302.5
8 | SABTRAK LTD | APPLIANCES | 42407202 |  | 37872852 | 13169223 | 13169223
9 | REEDPRICEMAN | OFFICE FURNITURE | 1492211413 |  | 802346094.5 | 422083323.75 | 422083323.75
|  | EQUIPMENT AND FURNISHING SUB TOTAL | 10339836673.06 | TO NEGOTIATE | 9421819406.81 | 6058019297.56 | 5279788095.25
|  | Equipment & Furnishing Variation@10% | 1033983667.306 | VARIATION 5% | 471090970.3405 | 302900964.878 | 263989404.7625
|  | TOTAL EQUIPMENT AND FURNISHING COST | 11373820340.366 |  | 9892910377.1505 | 6360920262.438 | 5543777500.0125
|  |  | 19026618100.413 |  | 14677027593.795 | 9830553365.0205 | 8422289574.0795
|  |  |  | DIFFERENCE | 4349590506.618 | 9196064735.3925 | 10604328526.3335
EQUIPMENT PAYMENT PLAN
|  | Initial Payment (15 days) 50% | 5686910170.183 |  | 4946455188.5752 | 3180460131.219 | 2771888750.0062
|  | Next Payment (60 days) 30% | 3412146102.1098 |  | 2967873113.1451 | 1908276078.7314 | 1663133250.0037
|  | Final Payment (Post Deployment) 20% | 2274764068.0732 |  | 1978582075.4301 | 1272184052.4876 | 1108755500.0025
SCENARIO TOTAL SUM
This is excludes all Preoperational cost
APPROXIMATE ESTIMATED COST OF MORTUARY
Total floor area of OPD IS 2,458
Total contract sum of OPD IS 1,176,578,029.99
Cost per m2 cost/are= N478,672.92
| Total floor area for mortuary is 500 M2 |  | TO BE REDESIGNED
Utilizing average cost Per Sq. metre of N400,000
This gives - N400,000 x 500 = N 200,000,000.00
Cost of constructing mortuary is N 250,000,000 - Estimated

## SOH PHASE PLANNING TEMPLATE (C)
STELLA OBASANJO HOSPITAL PHASE PLANNING
|  |  | FULL PROJECT 9-12 MONTHS | QUICK ACTION | Option 1 (9-12 months) | Option 2 (6-9 Months) | Option 3 (6-7 Months)
|  | Description | EASY PAYMENT PLAN |  | Full Project LESS ADMIN | OPD + DIAGNOSTICS + MORTUARY + INFRASTRUCTURE | OPD + DIAG STRIPPED DOWN
S/No. | CONTRACTOR | ITEMS
1 | A & K Construction Limited | OPD - Out Patient Department | 1176578029.99 |  | 1176578029.99 | 1176578029.99 | 1176578029.99
2 | A & K Construction Limited | IPD - In Patient Department | 3129724081.1 |  | 3129724081.1 | 1877834448.66 | 1564862040.55
3 | A & K Construction Limited | Administrative Block | 2400786761.68 |  | 0 | 0 | 0
4 | TO BE ADVISED - TBA | Mortuary (Estimate) | 250000000 |  | 250000000 | 250000000 | 0
|  | SUB TOTAL - CONSTRUCTION | 6957088872.77 | TO NEGOTIATE | 4556302111.09 | 3304412478.65 | 2741440070.54
|  | Construction Variation @10% | 695708887.277 | VARIATION 5% | 227815105.5545 | 165220623.9325 | 137072003.527
|  | Construction Total | 7652797760.047 |  | 4784117216.6445 | 3469633102.5825 | 2878512074.067
1 | SUDABELT MEDICAL CO. LTD | Lot 1 - Medical Equipment | 4135198000 |  | 4135198000 | 1566785650 | 1566785650
2 | SUDABELT MEDICAL CO. LTD | Lot 2 - Radiology | 2104552000 |  | 2104552000 | 2104552000 | 2104552000
3 | SUPREME MEDITECH LTD. | Lot 3 - Medical Gases | 648989222.31 |  | 648989222.31 | 648989222.31 | 0
4 | SUPREME MEDITECH LTD. | Lot 4 - Mortuary | 129241980 |  | 129241980 | 129241980 | 0
5 | SUDABELT MEDICAL CO. LTD | Lot 5 - Laboratory | 1090041596 |  | 1090041596 | 1090041596 | 1090041596
6 | REEDPRICEMAN | KITCHEN LAUNDRY TOOLS + FURNITURE | 339472422.5 |  | 339472422.5 | 0 | 0
7 | BLUEHUB LTD | IT EQUIPMENT AND AUDIOVISUALS | 357722837.25 |  | 134105239.5 | 83156302.5 | 83156302.5
8 | SABTRAK LTD | APPLIANCES | 42407202 |  | 35573814 | 10870185 | 10870185
9 | REEDPRICEMAN | OFFICE FURNITURE | 1492211413 |  | 809369069.5 | 429106298.75 | 429106298.75
|  | EQUIPMENT AND FURNISHING SUB TOTAL | 10339836673.06 | TO NEGOTIATE | 9426543343.81 | 6062743234.56 | 5284512032.25
|  | Equipment & Furnishing Variation@10% | 1033983667.306 | VARIATION 5% | 471327167.1905 | 303137161.728 | 264225601.6125
|  | TOTAL EQUIPMENT AND FURNISHING COST | 11373820340.366 |  | 9897870511.0005 | 6365880396.288 | 5548737633.8625
|  |  | 19026618100.413 |  | 14681987727.645 | 9835513498.8705 | 8427249707.9295
|  |  |  | DIFFERENCE | 4344630372.768 | 9191104601.5425 | 10599368392.4835
EQUIPMENT PAYMENT PLAN
|  | Initial Payment (15 days) 50% | 5686910170.183 |  | 4948935255.5002 | 3182940198.144 | 2774368816.9313
|  | Next Payment (60 days) 30% | 3412146102.1098 |  | 2969361153.3001 | 1909764118.8864 | 1664621290.1588
|  | Final Payment (Post Deployment) 20% | 2274764068.0732 |  | 1979574102.2001 | 1273176079.2576 | 1109747526.7725
SCENARIO TOTAL SUM
This is excludes all Preoperational cost
APPROXIMATE ESTIMATED COST OF MORTUARY
Total floor area of OPD IS 2,458
Total contract sum of OPD IS 1,176,578,029.99
Cost per m2 cost/are= N478,672.92
| Total floor area for mortuary is 500 M2 |  | TO BE REDESIGNED
Utilizing average cost Per Sq. metre of N400,000
This gives - N400,000 x 500 = N 200,000,000.00
Cost of constructing mortuary is N 250,000,000 - Estimated