## Sheet1
Sn | Task description | Location & Status
|  | MRI | CT | X-RAY | MAMMO
1 | Cable tray from SMDP room | Completed | Completed | Not started | Completed
2 | Vertical cable tray on finished wall | Not started | Not started | Not started | Not started
3 | Piping/cable tray location for ATS | Completed | NA | NA | NA
4 | Piping/cable tray location for AVR | Completed | NA | NA | NA
5 | Piping/cable tray location for UPS & battery | Completed | Completed | Completed | Completed
6 | Piping/cable tray location for Gear switch1 | Completed | NA | NA | NA
7 | Piping/cable tray location for Gear switch 2 | Completed | Completed | Not started | Completed
8 | Piping/cable tray location for Gear switch 3 | Completed | Completed | Not started | Completed
9 | Piping/cable tray location for indoor chiller & compressor | Completed | NA | Not started | NA
10 | Piping/cable tray location for outdoor chiller | Completed | NA | Not started | NA
11 | Piping/cable tray location for PDB /PDU | Completed | Completed | Not started | Completed
12 | Piping/cable tray location for MDB | Completed | Completed | Not started | Completed
13 | Piping/cable tray location for Manual change-over | Completed | Not started | NA | NA
14 | Piping/cable tray location for Inspector tool | Completed | Completed | Not started | Completed
15 | Piping/cable tray location for Earth bar | Completed | Completed | Not started | Completed
16 | Floor duct opening to control room | NA | Not started | Not started | Not started
17 | SEO (Sysytem Emergency On), X-ray light On & push button | Completed | Completed | Completed | Completed
18 | HVAC sytem | Not started | Completed | Completed | Completed
19 | Plumbing system (Floor drain & External chiller to compressor connection | Completed | NA | NA | NA
20 | Temperature sensor | Not started | Not started | Not started | Not started